## Agile Tasks
Task ID | Epic | Sprint Name | Team Member | Priority | Story Points | Task Status | Start Date | Due Date | Completion Date | Department | Risk Level | Estimated Hours | Actual Hours | Delay Reason | Sprint Start Date | Sprint End Date | Cycle Time Days | Is Overdue | Completed Flag
APT-0001 | Data Quality Remediation | Sprint 04 - 2025 | Rohan Gupta | Low | 3 | Testing | 2025-02-16 | 2025-02-23 |  | Data Analytics | Medium | 11 | 13 | UAT Feedback | 2025-02-16 | 2025-03-01 | 0 | Yes | 0
APT-0002 | Customer Onboarding Automation | Sprint 02 - 2025 | Aarav Mehta | Low | 8 | Done | 2025-01-23 | 2025-01-27 | 2025-01-29 | Operations | High | 54 | 68 | Environment Issue | 2025-01-19 | 2025-02-01 | 5 | Yes | 1
APT-0003 | Stakeholder Notification Service | Sprint 11 - 2025 | Vikram Singh | High | 5 | Done | 2025-05-31 | 2025-06-10 | 2025-06-09 | QA | Low | 20 | 23 | None | 2025-05-25 | 2025-06-07 | 8 | No | 1
APT-0004 | Sprint Reporting Hub | Sprint 03 - 2025 | Arjun Menon | Medium | 3 | Done | 2025-02-09 | 2025-02-20 | 2025-02-21 | Customer Success | Low | 12 | 15 | Resource Constraint | 2025-02-02 | 2025-02-15 | 11 | Yes | 1
APT-0005 | Backlog Prioritization Framework | Sprint 09 - 2025 | Zoya Fernandes | Medium | 2 | Done | 2025-04-29 | 2025-05-08 | 2025-05-08 | QA | Low | 8 | 9 | None | 2025-04-27 | 2025-05-10 | 8 | No | 1
APT-0006 | Billing Workflow Optimization | Sprint 02 - 2025 | Isha Sharma | Low | 13 | Done | 2025-01-22 | 2025-02-01 | 2025-01-30 | QA | Medium | 76 | 74 | None | 2025-01-19 | 2025-02-01 | 7 | No | 1
APT-0007 | Stakeholder Notification Service | Sprint 11 - 2025 | Rohan Gupta | Critical | 3 | Done | 2025-05-27 | 2025-06-03 | 2025-06-03 | Engineering | Low | 16 | 18 | None | 2025-05-25 | 2025-06-07 | 6 | No | 1
APT-0008 | Stakeholder Notification Service | Sprint 05 - 2025 | Arjun Menon | Medium | 8 | Testing | 2025-03-10 | 2025-03-18 |  | Data Analytics | High | 59 | 58 | Environment Issue | 2025-03-02 | 2025-03-15 | 0 | Yes | 0
APT-0009 | Data Quality Remediation | Sprint 10 - 2025 | Isha Sharma | Medium | 1 | Done | 2025-05-14 | 2025-05-21 | 2025-05-19 | Customer Success | Medium | 5 | 6 | None | 2025-05-11 | 2025-05-24 | 4 | No | 1
APT-0010 | Mobile Experience Improvements | Sprint 07 - 2025 | Sara Thomas | Low | 8 | Done | 2025-04-05 | 2025-04-13 | 2025-04-14 | Product | High | 53 | 71 | Requirement Change | 2025-03-30 | 2025-04-12 | 8 | Yes | 1
APT-0011 | User Access Governance | Sprint 06 - 2025 | Sara Thomas | Medium | 1 | Done | 2025-03-19 | 2025-03-27 | 2025-03-26 | Operations | Medium | 4 | 4 | None | 2025-03-16 | 2025-03-29 | 6 | No | 1
APT-0012 | Data Quality Remediation | Sprint 05 - 2025 | Vikram Singh | High | 8 | Done | 2025-03-06 | 2025-03-15 | 2025-03-15 | Operations | Low | 32 | 31 | None | 2025-03-02 | 2025-03-15 | 8 | No | 1
APT-0013 | Sprint Reporting Hub | Sprint 10 - 2025 | Rohan Gupta | Medium | 3 | Done | 2025-05-17 | 2025-05-25 | 2025-05-25 | Operations | Medium | 18 | 24 | None | 2025-05-11 | 2025-05-24 | 7 | No | 1
APT-0014 | Backlog Prioritization Framework | Sprint 09 - 2025 | Rohan Gupta | Low | 8 | To Do | 2025-04-29 | 2025-05-05 |  | Product | Low | 44 | 0 | Resource Constraint | 2025-04-27 | 2025-05-10 | 0 | Yes | 0
APT-0015 | API Reliability Upgrade | Sprint 07 - 2025 | Zoya Fernandes | Critical | 8 | Testing | 2025-04-07 | 2025-04-17 |  | Product | Low | 34 | 33 | Environment Issue | 2025-03-30 | 2025-04-12 | 0 | Yes | 0
APT-0016 | Sprint Reporting Hub | Sprint 12 - 2025 | Vikram Singh | High | 5 | Done | 2025-06-14 | 2025-06-21 | 2025-06-21 | Customer Success | Medium | 30 | 33 | None | 2025-06-08 | 2025-06-21 | 6 | No | 1
APT-0017 | Operations SLA Dashboard | Sprint 03 - 2025 | Isha Sharma | Medium | 13 | Done | 2025-02-05 | 2025-02-12 | 2025-02-14 | Engineering | Low | 50 | 48 | Requirement Change | 2025-02-02 | 2025-02-15 | 8 | Yes | 1
APT-0018 | Data Quality Remediation | Sprint 10 - 2025 | Zoya Fernandes | Low | 3 | Testing | 2025-05-13 | 2025-05-25 |  | Product | High | 20 | 18 | Environment Issue | 2025-05-11 | 2025-05-24 | 0 | Yes | 0
APT-0019 | Operations SLA Dashboard | Sprint 02 - 2025 | Meera Nair | High | 8 | Done | 2025-01-25 | 2025-01-28 | 2025-01-28 | Operations | Low | 45 | 56 | None | 2025-01-19 | 2025-02-01 | 2 | No | 1
APT-0020 | Backlog Prioritization Framework | Sprint 09 - 2025 | Arjun Menon | Medium | 5 | Done | 2025-05-05 | 2025-05-10 | 2025-05-11 | QA | Low | 20 | 22 | Scope Clarification | 2025-04-27 | 2025-05-10 | 5 | Yes | 1
APT-0021 | Sprint Reporting Hub | Sprint 10 - 2025 | Kabir Khan | Medium | 5 | In Progress | 2025-05-18 | 2025-05-27 |  | Operations | Low | 26 | 14 | Scope Clarification | 2025-05-11 | 2025-05-24 | 0 | Yes | 0
APT-0022 | Stakeholder Notification Service | Sprint 03 - 2025 | Dev Patel | Low | 3 | Done | 2025-02-06 | 2025-02-13 | 2025-02-14 | QA | Low | 16 | 14 | Scope Clarification | 2025-02-02 | 2025-02-15 | 7 | Yes | 1
APT-0023 | Billing Workflow Optimization | Sprint 12 - 2025 | Ananya Rao | Medium | 5 | Done | 2025-06-15 | 2025-06-20 | 2025-06-21 | Customer Success | Medium | 22 | 30 | Environment Issue | 2025-06-08 | 2025-06-21 | 5 | Yes | 1
APT-0024 | Backlog Prioritization Framework | Sprint 12 - 2025 | Ananya Rao | Medium | 8 | In Progress | 2025-06-11 | 2025-06-17 |  | Product | Medium | 51 | 39 | Dependency Blocker | 2025-06-08 | 2025-06-21 | 0 | Yes | 0
APT-0025 | Mobile Experience Improvements | Sprint 09 - 2025 | Vikram Singh | Medium | 5 | Done | 2025-05-03 | 2025-05-07 | 2025-05-09 | Engineering | Medium | 31 | 43 | Requirement Change | 2025-04-27 | 2025-05-10 | 5 | Yes | 1
APT-0026 | Billing Workflow Optimization | Sprint 04 - 2025 | Zoya Fernandes | Medium | 5 | Done | 2025-02-18 | 2025-02-27 | 2025-02-25 | Product | Low | 27 | 33 | None | 2025-02-16 | 2025-03-01 | 6 | No | 1
APT-0027 | Backlog Prioritization Framework | Sprint 06 - 2025 | Kabir Khan | Medium | 3 | Done | 2025-03-24 | 2025-03-30 | 2025-03-28 | Engineering | Low | 16 | 18 | None | 2025-03-16 | 2025-03-29 | 3 | No | 1
APT-0028 | API Reliability Upgrade | Sprint 01 - 2025 | Vikram Singh | Medium | 2 | Done | 2025-01-05 | 2025-01-13 | 2025-01-11 | Engineering | Medium | 13 | 16 | None | 2025-01-05 | 2025-01-18 | 5 | No | 1
APT-0029 | API Reliability Upgrade | Sprint 07 - 2025 | Zoya Fernandes | Low | 5 | Done | 2025-04-03 | 2025-04-08 | 2025-04-10 | Operations | Medium | 31 | 35 | UAT Feedback | 2025-03-30 | 2025-04-12 | 6 | Yes | 1
APT-0030 | Billing Workflow Optimization | Sprint 05 - 2025 | Kabir Khan | High | 5 | Done | 2025-03-05 | 2025-03-12 | 2025-03-12 | Operations | Medium | 23 | 24 | None | 2025-03-02 | 2025-03-15 | 6 | No | 1
APT-0031 | Sprint Reporting Hub | Sprint 12 - 2025 | Sara Thomas | Medium | 5 | In Progress | 2025-06-11 | 2025-06-19 |  | Data Analytics | Medium | 21 | 10 | UAT Feedback | 2025-06-08 | 2025-06-21 | 0 | Yes | 0
APT-0032 | User Access Governance | Sprint 05 - 2025 | Dev Patel | Medium | 3 | Done | 2025-03-04 | 2025-03-12 | 2025-03-13 | Data Analytics | Low | 10 | 11 | Scope Clarification | 2025-03-02 | 2025-03-15 | 8 | Yes | 1
APT-0033 | API Reliability Upgrade | Sprint 11 - 2025 | Neha Verma | Medium | 3 | Done | 2025-05-29 | 2025-06-02 | 2025-06-02 | Operations | Low | 15 | 14 | None | 2025-05-25 | 2025-06-07 | 3 | No | 1
APT-0034 | Data Quality Remediation | Sprint 11 - 2025 | Vikram Singh | Critical | 2 | Done | 2025-05-29 | 2025-06-03 | 2025-06-05 | QA | Low | 13 | 15 | UAT Feedback | 2025-05-25 | 2025-06-07 | 6 | Yes | 1
APT-0035 | User Access Governance | Sprint 07 - 2025 | Ananya Rao | Medium | 3 | Done | 2025-04-06 | 2025-04-16 | 2025-04-16 | Engineering | High | 16 | 18 | None | 2025-03-30 | 2025-04-12 | 9 | No | 1
APT-0036 | Billing Workflow Optimization | Sprint 08 - 2025 | Sara Thomas | Medium | 2 | Done | 2025-04-16 | 2025-04-20 | 2025-04-20 | QA | Medium | 12 | 13 | None | 2025-04-13 | 2025-04-26 | 3 | No | 1
APT-0037 | Sprint Reporting Hub | Sprint 09 - 2025 | Isha Sharma | Medium | 3 | Done | 2025-05-05 | 2025-05-15 | 2025-05-13 | Product | Low | 11 | 10 | None | 2025-04-27 | 2025-05-10 | 7 | No | 1
APT-0038 | Backlog Prioritization Framework | Sprint 05 - 2025 | Isha Sharma | Medium | 3 | Done | 2025-03-04 | 2025-03-14 | 2025-03-16 | Operations | Low | 13 | 16 | Scope Clarification | 2025-03-02 | 2025-03-15 | 11 | Yes | 1
APT-0039 | Backlog Prioritization Framework | Sprint 07 - 2025 | Isha Sharma | Medium | 3 | Testing | 2025-04-05 | 2025-04-11 |  | Engineering | Medium | 15 | 13 | UAT Feedback | 2025-03-30 | 2025-04-12 | 0 | Yes | 0
APT-0040 | API Reliability Upgrade | Sprint 11 - 2025 | Aarav Mehta | High | 3 | Done | 2025-05-30 | 2025-06-03 | 2025-06-09 | Data Analytics | High | 21 | 23 | Scope Clarification | 2025-05-25 | 2025-06-07 | 9 | Yes | 1
APT-0041 | Customer Onboarding Automation | Sprint 07 - 2025 | Zoya Fernandes | Medium | 1 | Done | 2025-03-31 | 2025-04-03 | 2025-04-03 | Customer Success | Medium | 7 | 9 | None | 2025-03-30 | 2025-04-12 | 2 | No | 1
APT-0042 | Customer Onboarding Automation | Sprint 03 - 2025 | Zoya Fernandes | High | 3 | Done | 2025-02-06 | 2025-02-11 | 2025-02-11 | Engineering | High | 16 | 23 | None | 2025-02-02 | 2025-02-15 | 4 | No | 1
APT-0043 | Operations SLA Dashboard | Sprint 08 - 2025 | Ananya Rao | Low | 5 | To Do | 2025-04-18 | 2025-04-28 |  | Customer Success | Medium | 23 | 0 | Scope Clarification | 2025-04-13 | 2025-04-26 | 0 | Yes | 0
APT-0044 | User Access Governance | Sprint 06 - 2025 | Kabir Khan | Low | 2 | Done | 2025-03-18 | 2025-03-28 | 2025-03-30 | Product | Low | 9 | 8 | Scope Clarification | 2025-03-16 | 2025-03-29 | 11 | Yes | 1
APT-0045 | Sprint Reporting Hub | Sprint 11 - 2025 | Rohan Gupta | Critical | 1 | Done | 2025-06-02 | 2025-06-12 | 2025-06-14 | Product | Low | 5 | 5 | UAT Feedback | 2025-05-25 | 2025-06-07 | 11 | Yes | 1
APT-0046 | Mobile Experience Improvements | Sprint 08 - 2025 | Ananya Rao | High | 2 | Done | 2025-04-18 | 2025-04-29 | 2025-05-01 | Data Analytics | Low | 7 | 9 | Scope Clarification | 2025-04-13 | 2025-04-26 | 12 | Yes | 1
APT-0047 | API Reliability Upgrade | Sprint 06 - 2025 | Neha Verma | Low | 1 | In Progress | 2025-03-18 | 2025-03-24 |  | Product | High | 6 | 3 | Scope Clarification | 2025-03-16 | 2025-03-29 | 0 | Yes | 0
APT-0048 | Customer Onboarding Automation | Sprint 02 - 2025 | Sara Thomas | Low | 8 | Testing | 2025-01-23 | 2025-02-01 |  | Operations | High | 35 | 43 | Requirement Change | 2025-01-19 | 2025-02-01 | 0 | Yes | 0
APT-0049 | Sprint Reporting Hub | Sprint 02 - 2025 | Meera Nair | Low | 5 | Done | 2025-01-21 | 2025-01-25 | 2025-01-27 | Customer Success | Medium | 25 | 31 | Dependency Blocker | 2025-01-19 | 2025-02-01 | 5 | Yes | 1
APT-0050 | Operations SLA Dashboard | Sprint 12 - 2025 | Arjun Menon | Critical | 5 | Done | 2025-06-12 | 2025-06-19 | 2025-06-20 | Operations | High | 30 | 35 | Scope Clarification | 2025-06-08 | 2025-06-21 | 7 | Yes | 1
APT-0051 | Stakeholder Notification Service | Sprint 02 - 2025 | Rohan Gupta | High | 3 | To Do | 2025-01-25 | 2025-01-31 |  | Engineering | Medium | 17 | 0 | Requirement Change | 2025-01-19 | 2025-02-01 | 0 | Yes | 0
APT-0052 | Billing Workflow Optimization | Sprint 03 - 2025 | Meera Nair | Low | 3 | Done | 2025-02-06 | 2025-02-13 | 2025-02-13 | Operations | Low | 10 | 10 | None | 2025-02-02 | 2025-02-15 | 6 | No | 1
APT-0053 | Billing Workflow Optimization | Sprint 11 - 2025 | Ananya Rao | High | 2 | Done | 2025-05-25 | 2025-06-06 | 2025-06-06 | Customer Success | Low | 10 | 11 | None | 2025-05-25 | 2025-06-07 | 11 | No | 1
APT-0054 | Stakeholder Notification Service | Sprint 09 - 2025 | Meera Nair | Low | 8 | Done | 2025-04-30 | 2025-05-05 | 2025-05-05 | Operations | High | 47 | 57 | None | 2025-04-27 | 2025-05-10 | 4 | No | 1
APT-0055 | Customer Onboarding Automation | Sprint 11 - 2025 | Dev Patel | Medium | 1 | Done | 2025-05-26 | 2025-06-04 | 2025-06-05 | Engineering | Low | 4 | 4 | Resource Constraint | 2025-05-25 | 2025-06-07 | 9 | Yes | 1
APT-0056 | Data Quality Remediation | Sprint 12 - 2025 | Zoya Fernandes | Low | 3 | Testing | 2025-06-15 | 2025-06-23 |  | Product | Medium | 18 | 14 | Scope Clarification | 2025-06-08 | 2025-06-21 | 0 | Yes | 0
APT-0057 | Backlog Prioritization Framework | Sprint 01 - 2025 | Kabir Khan | High | 5 | Testing | 2025-01-09 | 2025-01-14 |  | Engineering | Low | 18 | 15 | Requirement Change | 2025-01-05 | 2025-01-18 | 0 | Yes | 0
APT-0058 | Mobile Experience Improvements | Sprint 07 - 2025 | Neha Verma | High | 3 | Done | 2025-03-30 | 2025-04-09 | 2025-04-09 | Engineering | Medium | 16 | 17 | None | 2025-03-30 | 2025-04-12 | 9 | No | 1
APT-0059 | Operations SLA Dashboard | Sprint 11 - 2025 | Arjun Menon | Medium | 8 | Done | 2025-05-31 | 2025-06-06 | 2025-06-06 | Engineering | Medium | 53 | 60 | None | 2025-05-25 | 2025-06-07 | 5 | No | 1
APT-0060 | API Reliability Upgrade | Sprint 11 - 2025 | Ananya Rao | Low | 2 | Testing | 2025-05-29 | 2025-06-08 |  | Operations | Medium | 12 | 12 | Requirement Change | 2025-05-25 | 2025-06-07 | 0 | Yes | 0
APT-0061 | Billing Workflow Optimization | Sprint 09 - 2025 | Meera Nair | High | 3 | Done | 2025-05-01 | 2025-05-05 | 2025-05-05 | Engineering | High | 21 | 27 | None | 2025-04-27 | 2025-05-10 | 3 | No | 1
APT-0062 | Backlog Prioritization Framework | Sprint 05 - 2025 | Zoya Fernandes | Medium | 8 | Done | 2025-03-10 | 2025-03-17 | 2025-03-17 | Operations | Low | 41 | 45 | None | 2025-03-02 | 2025-03-15 | 6 | No | 1
APT-0063 | Stakeholder Notification Service | Sprint 07 - 2025 | Ananya Rao | High | 8 | Done | 2025-04-05 | 2025-04-12 | 2025-04-11 | Operations | Medium | 36 | 49 | None | 2025-03-30 | 2025-04-12 | 5 | No | 1
APT-0064 | Operations SLA Dashboard | Sprint 10 - 2025 | Aarav Mehta | Critical | 8 | Done | 2025-05-17 | 2025-05-29 | 2025-05-27 | Customer Success | Low | 56 | 58 | None | 2025-05-11 | 2025-05-24 | 9 | No | 1
APT-0065 | Billing Workflow Optimization | Sprint 03 - 2025 | Zoya Fernandes | High | 3 | Done | 2025-02-07 | 2025-02-14 | 2025-02-16 | QA | Low | 17 | 19 | Environment Issue | 2025-02-02 | 2025-02-15 | 8 | Yes | 1
APT-0066 | API Reliability Upgrade | Sprint 04 - 2025 | Kabir Khan | Low | 2 | Done | 2025-02-19 | 2025-02-28 | 2025-02-28 | Customer Success | Low | 9 | 11 | None | 2025-02-16 | 2025-03-01 | 8 | No | 1
APT-0067 | API Reliability Upgrade | Sprint 09 - 2025 | Meera Nair | Medium | 5 | Testing | 2025-05-05 | 2025-05-08 |  | Customer Success | Low | 27 | 24 | Environment Issue | 2025-04-27 | 2025-05-10 | 0 | Yes | 0
APT-0068 | Billing Workflow Optimization | Sprint 08 - 2025 | Ananya Rao | High | 13 | Done | 2025-04-17 | 2025-04-26 | 2025-04-26 | Customer Success | Low | 72 | 83 | None | 2025-04-13 | 2025-04-26 | 8 | No | 1
APT-0069 | Stakeholder Notification Service | Sprint 10 - 2025 | Ananya Rao | High | 5 | To Do | 2025-05-13 | 2025-05-19 |  | Engineering | Low | 23 | 0 | Scope Clarification | 2025-05-11 | 2025-05-24 | 0 | Yes | 0
APT-0070 | Data Quality Remediation | Sprint 10 - 2025 | Meera Nair | Critical | 5 | In Progress | 2025-05-16 | 2025-05-24 |  | QA | Low | 34 | 20 | Dependency Blocker | 2025-05-11 | 2025-05-24 | 0 | Yes | 0
APT-0071 | Stakeholder Notification Service | Sprint 01 - 2025 | Neha Verma | High | 5 | Done | 2025-01-09 | 2025-01-19 | 2025-01-20 | QA | Low | 28 | 28 | Scope Clarification | 2025-01-05 | 2025-01-18 | 10 | Yes | 1
APT-0072 | Billing Workflow Optimization | Sprint 11 - 2025 | Meera Nair | Low | 5 | Done | 2025-05-29 | 2025-06-02 | 2025-06-02 | Engineering | Low | 18 | 19 | None | 2025-05-25 | 2025-06-07 | 3 | No | 1
APT-0073 | User Access Governance | Sprint 02 - 2025 | Neha Verma | Medium | 2 | Done | 2025-01-24 | 2025-01-30 | 2025-01-30 | Engineering | High | 13 | 17 | None | 2025-01-19 | 2025-02-01 | 5 | No | 1
APT-0074 | User Access Governance | Sprint 06 - 2025 | Zoya Fernandes | High | 8 | Done | 2025-03-18 | 2025-03-22 | 2025-03-23 | QA | Medium | 51 | 59 | Scope Clarification | 2025-03-16 | 2025-03-29 | 4 | Yes | 1
APT-0075 | Mobile Experience Improvements | Sprint 05 - 2025 | Sara Thomas | Medium | 3 | To Do | 2025-03-03 | 2025-03-12 |  | Engineering | Low | 12 | 0 | UAT Feedback | 2025-03-02 | 2025-03-15 | 0 | Yes | 0
APT-0076 | Sprint Reporting Hub | Sprint 11 - 2025 | Vikram Singh | Medium | 5 | Done | 2025-05-26 | 2025-05-30 | 2025-05-31 | Engineering | High | 33 | 36 | Environment Issue | 2025-05-25 | 2025-06-07 | 4 | Yes | 1
APT-0077 | Backlog Prioritization Framework | Sprint 11 - 2025 | Ananya Rao | Medium | 8 | In Progress | 2025-05-30 | 2025-06-09 |  | Customer Success | Low | 41 | 30 | Environment Issue | 2025-05-25 | 2025-06-07 | 0 | Yes | 0
APT-0078 | Customer Onboarding Automation | Sprint 03 - 2025 | Vikram Singh | High | 8 | Done | 2025-02-07 | 2025-02-13 | 2025-02-14 | Customer Success | Medium | 39 | 53 | Requirement Change | 2025-02-02 | 2025-02-15 | 6 | Yes | 1
APT-0079 | Customer Onboarding Automation | Sprint 05 - 2025 | Arjun Menon | Low | 3 | Testing | 2025-03-04 | 2025-03-16 |  | QA | High | 17 | 18 | Requirement Change | 2025-03-02 | 2025-03-15 | 0 | Yes | 0
APT-0080 | Billing Workflow Optimization | Sprint 12 - 2025 | Neha Verma | Medium | 1 | Done | 2025-06-12 | 2025-06-23 | 2025-06-23 | Operations | High | 8 | 9 | None | 2025-06-08 | 2025-06-21 | 10 | No | 1
APT-0081 | User Access Governance | Sprint 07 - 2025 | Arjun Menon | Medium | 5 | Done | 2025-04-06 | 2025-04-15 | 2025-04-17 | Customer Success | Low | 18 | 19 | Environment Issue | 2025-03-30 | 2025-04-12 | 10 | Yes | 1
APT-0082 | Stakeholder Notification Service | Sprint 10 - 2025 | Aarav Mehta | Medium | 8 | Done | 2025-05-14 | 2025-05-25 | 2025-05-25 | QA | Low | 29 | 28 | None | 2025-05-11 | 2025-05-24 | 10 | No | 1
APT-0083 | Customer Onboarding Automation | Sprint 08 - 2025 | Sara Thomas | Medium | 3 | Done | 2025-04-13 | 2025-04-19 | 2025-04-19 | Operations | Medium | 15 | 16 | None | 2025-04-13 | 2025-04-26 | 5 | No | 1
APT-0084 | Backlog Prioritization Framework | Sprint 03 - 2025 | Kabir Khan | Medium | 2 | Done | 2025-02-06 | 2025-02-09 | 2025-02-10 | Engineering | High | 14 | 19 | Requirement Change | 2025-02-02 | 2025-02-15 | 3 | Yes | 1
APT-0085 | Data Quality Remediation | Sprint 03 - 2025 | Rohan Gupta | Medium | 3 | Done | 2025-02-05 | 2025-02-09 | 2025-02-11 | QA | Low | 13 | 14 | Requirement Change | 2025-02-02 | 2025-02-15 | 5 | Yes | 1
APT-0086 | Mobile Experience Improvements | Sprint 03 - 2025 | Isha Sharma | High | 2 | Done | 2025-02-10 | 2025-02-14 | 2025-02-14 | Data Analytics | Medium | 12 | 14 | None | 2025-02-02 | 2025-02-15 | 3 | No | 1
APT-0087 | Mobile Experience Improvements | Sprint 04 - 2025 | Ananya Rao | Medium | 3 | Done | 2025-02-19 | 2025-03-02 | 2025-03-05 | Data Analytics | Medium | 17 | 16 | Resource Constraint | 2025-02-16 | 2025-03-01 | 13 | Yes | 1
APT-0088 | Customer Onboarding Automation | Sprint 12 - 2025 | Zoya Fernandes | Medium | 8 | In Progress | 2025-06-14 | 2025-06-22 |  | Engineering | Low | 30 | 11 | Environment Issue | 2025-06-08 | 2025-06-21 | 0 | Yes | 0
APT-0089 | Mobile Experience Improvements | Sprint 10 - 2025 | Dev Patel | Low | 3 | Done | 2025-05-13 | 2025-05-23 | 2025-05-25 | Customer Success | Medium | 17 | 15 | UAT Feedback | 2025-05-11 | 2025-05-24 | 11 | Yes | 1
APT-0090 | Mobile Experience Improvements | Sprint 06 - 2025 | Sara Thomas | High | 5 | Done | 2025-03-16 | 2025-03-28 | 2025-03-30 | Operations | Low | 32 | 38 | Requirement Change | 2025-03-16 | 2025-03-29 | 13 | Yes | 1
APT-0091 | Billing Workflow Optimization | Sprint 06 - 2025 | Dev Patel | Critical | 3 | Done | 2025-03-16 | 2025-03-20 | 2025-03-18 | Product | Low | 18 | 17 | None | 2025-03-16 | 2025-03-29 | 1 | No | 1
APT-0092 | Customer Onboarding Automation | Sprint 12 - 2025 | Vikram Singh | Low | 3 | Done | 2025-06-11 | 2025-06-20 | 2025-06-20 | Engineering | Low | 14 | 12 | None | 2025-06-08 | 2025-06-21 | 8 | No | 1
APT-0093 | Data Quality Remediation | Sprint 09 - 2025 | Zoya Fernandes | Medium | 3 | Done | 2025-05-02 | 2025-05-05 | 2025-05-07 | QA | Low | 10 | 9 | Resource Constraint | 2025-04-27 | 2025-05-10 | 4 | Yes | 1
APT-0094 | Backlog Prioritization Framework | Sprint 11 - 2025 | Rohan Gupta | Low | 2 | Done | 2025-05-27 | 2025-05-30 | 2025-05-30 | Operations | Low | 8 | 10 | None | 2025-05-25 | 2025-06-07 | 2 | No | 1
APT-0095 | Customer Onboarding Automation | Sprint 05 - 2025 | Isha Sharma | Medium | 1 | Done | 2025-03-09 | 2025-03-13 | 2025-03-12 | Operations | Medium | 6 | 7 | None | 2025-03-02 | 2025-03-15 | 2 | No | 1
APT-0096 | Sprint Reporting Hub | Sprint 07 - 2025 | Arjun Menon | High | 2 | Done | 2025-04-01 | 2025-04-04 | 2025-04-04 | Engineering | Medium | 13 | 15 | None | 2025-03-30 | 2025-04-12 | 2 | No | 1
APT-0097 | Customer Onboarding Automation | Sprint 10 - 2025 | Sara Thomas | Critical | 5 | Done | 2025-05-19 | 2025-05-29 | 2025-05-30 | Operations | Low | 30 | 26 | Environment Issue | 2025-05-11 | 2025-05-24 | 10 | Yes | 1
APT-0098 | Stakeholder Notification Service | Sprint 12 - 2025 | Neha Verma | High | 3 | To Do | 2025-06-14 | 2025-06-17 |  | Data Analytics | Medium | 17 | 0 | Requirement Change | 2025-06-08 | 2025-06-21 | 0 | Yes | 0
APT-0099 | Mobile Experience Improvements | Sprint 01 - 2025 | Vikram Singh | Critical | 13 | In Progress | 2025-01-10 | 2025-01-22 |  | Customer Success | High | 72 | 38 | Environment Issue | 2025-01-05 | 2025-01-18 | 0 | Yes | 0
APT-0100 | Mobile Experience Improvements | Sprint 03 - 2025 | Dev Patel | Medium | 2 | Done | 2025-02-04 | 2025-02-15 | 2025-02-18 | QA | High | 14 | 19 | Scope Clarification | 2025-02-02 | 2025-02-15 | 13 | Yes | 1
APT-0101 | Backlog Prioritization Framework | Sprint 04 - 2025 | Isha Sharma | Medium | 3 | Done | 2025-02-24 | 2025-02-28 | 2025-02-28 | QA | High | 21 | 32 | None | 2025-02-16 | 2025-03-01 | 3 | No | 1
APT-0102 | Mobile Experience Improvements | Sprint 05 - 2025 | Sara Thomas | Medium | 5 | In Progress | 2025-03-09 | 2025-03-12 |  | Product | Medium | 23 | 10 | Requirement Change | 2025-03-02 | 2025-03-15 | 0 | Yes | 0
APT-0103 | Sprint Reporting Hub | Sprint 09 - 2025 | Isha Sharma | High | 3 | Done | 2025-04-27 | 2025-05-02 | 2025-05-02 | Product | Medium | 20 | 23 | None | 2025-04-27 | 2025-05-10 | 4 | No | 1
APT-0104 | Data Quality Remediation | Sprint 11 - 2025 | Dev Patel | Low | 3 | Done | 2025-05-26 | 2025-06-04 | 2025-06-04 | Data Analytics | Medium | 14 | 15 | None | 2025-05-25 | 2025-06-07 | 8 | No | 1
APT-0105 | Data Quality Remediation | Sprint 10 - 2025 | Arjun Menon | High | 3 | Done | 2025-05-18 | 2025-05-27 | 2025-05-29 | Data Analytics | Medium | 15 | 14 | Resource Constraint | 2025-05-11 | 2025-05-24 | 10 | Yes | 1
APT-0106 | Billing Workflow Optimization | Sprint 07 - 2025 | Vikram Singh | Low | 8 | To Do | 2025-04-01 | 2025-04-08 |  | Engineering | Low | 27 | 0 | Dependency Blocker | 2025-03-30 | 2025-04-12 | 0 | Yes | 0
APT-0107 | Customer Onboarding Automation | Sprint 03 - 2025 | Neha Verma | Low | 2 | In Progress | 2025-02-03 | 2025-02-11 |  | Engineering | Low | 7 | 4 | Requirement Change | 2025-02-02 | 2025-02-15 | 0 | Yes | 0
APT-0108 | User Access Governance | Sprint 01 - 2025 | Kabir Khan | High | 2 | Done | 2025-01-11 | 2025-01-15 | 2025-01-15 | Data Analytics | Medium | 10 | 13 | None | 2025-01-05 | 2025-01-18 | 3 | No | 1
APT-0109 | API Reliability Upgrade | Sprint 11 - 2025 | Kabir Khan | High | 13 | Done | 2025-06-01 | 2025-06-10 | 2025-06-12 | QA | Low | 69 | 71 | UAT Feedback | 2025-05-25 | 2025-06-07 | 10 | Yes | 1
APT-0110 | Sprint Reporting Hub | Sprint 06 - 2025 | Sara Thomas | Medium | 1 | Testing | 2025-03-20 | 2025-03-26 |  | Customer Success | Medium | 4 | 5 | Dependency Blocker | 2025-03-16 | 2025-03-29 | 0 | Yes | 0
APT-0111 | Billing Workflow Optimization | Sprint 05 - 2025 | Zoya Fernandes | Medium | 2 | Done | 2025-03-08 | 2025-03-20 | 2025-03-23 | Customer Success | Medium | 11 | 14 | Environment Issue | 2025-03-02 | 2025-03-15 | 14 | Yes | 1
APT-0112 | Stakeholder Notification Service | Sprint 04 - 2025 | Zoya Fernandes | Low | 2 | Testing | 2025-02-24 | 2025-03-05 |  | Customer Success | High | 8 | 8 | Dependency Blocker | 2025-02-16 | 2025-03-01 | 0 | Yes | 0
APT-0113 | Sprint Reporting Hub | Sprint 10 - 2025 | Sara Thomas | Medium | 3 | Testing | 2025-05-16 | 2025-05-27 |  | Product | Low | 15 | 12 | Environment Issue | 2025-05-11 | 2025-05-24 | 0 | Yes | 0
APT-0114 | Backlog Prioritization Framework | Sprint 09 - 2025 | Vikram Singh | Low | 8 | Testing | 2025-05-02 | 2025-05-12 |  | Data Analytics | Medium | 30 | 23 | Environment Issue | 2025-04-27 | 2025-05-10 | 0 | Yes | 0
APT-0115 | Stakeholder Notification Service | Sprint 02 - 2025 | Arjun Menon | Low | 3 | To Do | 2025-01-21 | 2025-01-30 |  | QA | Medium | 14 | 0 | UAT Feedback | 2025-01-19 | 2025-02-01 | 0 | Yes | 0
APT-0116 | Stakeholder Notification Service | Sprint 12 - 2025 | Meera Nair | Medium | 5 | Done | 2025-06-13 | 2025-06-25 | 2025-06-24 | Engineering | High | 34 | 51 | None | 2025-06-08 | 2025-06-21 | 10 | No | 1
APT-0117 | API Reliability Upgrade | Sprint 11 - 2025 | Meera Nair | Low | 1 | Done | 2025-05-27 | 2025-06-08 | 2025-06-08 | Product | Low | 4 | 3 | None | 2025-05-25 | 2025-06-07 | 11 | No | 1
APT-0118 | Customer Onboarding Automation | Sprint 03 - 2025 | Arjun Menon | Medium | 5 | In Progress | 2025-02-10 | 2025-02-15 |  | Customer Success | Medium | 28 | 12 | Dependency Blocker | 2025-02-02 | 2025-02-15 | 0 | Yes | 0
APT-0119 | Backlog Prioritization Framework | Sprint 04 - 2025 | Kabir Khan | High | 1 | Done | 2025-02-17 | 2025-03-01 | 2025-03-02 | QA | Medium | 7 | 8 | Requirement Change | 2025-02-16 | 2025-03-01 | 12 | Yes | 1
APT-0120 | Data Quality Remediation | Sprint 11 - 2025 | Dev Patel | High | 2 | Done | 2025-05-25 | 2025-05-29 | 2025-05-29 | Customer Success | Low | 9 | 10 | None | 2025-05-25 | 2025-06-07 | 3 | No | 1
APT-0121 | Operations SLA Dashboard | Sprint 08 - 2025 | Dev Patel | High | 5 | Done | 2025-04-17 | 2025-04-28 | 2025-04-29 | Customer Success | High | 41 | 59 | Environment Issue | 2025-04-13 | 2025-04-26 | 11 | Yes | 1
APT-0122 | Sprint Reporting Hub | Sprint 08 - 2025 | Dev Patel | Medium | 3 | In Progress | 2025-04-20 | 2025-04-29 |  | Operations | Low | 10 | 8 | Scope Clarification | 2025-04-13 | 2025-04-26 | 0 | Yes | 0
APT-0123 | Mobile Experience Improvements | Sprint 04 - 2025 | Vikram Singh | High | 8 | In Progress | 2025-02-17 | 2025-02-23 |  | Customer Success | Medium | 39 | 22 | Dependency Blocker | 2025-02-16 | 2025-03-01 | 0 | Yes | 0
APT-0124 | Operations SLA Dashboard | Sprint 11 - 2025 | Rohan Gupta | High | 2 | To Do | 2025-05-31 | 2025-06-12 |  | Data Analytics | Medium | 15 | 0 | UAT Feedback | 2025-05-25 | 2025-06-07 | 0 | Yes | 0
APT-0125 | Sprint Reporting Hub | Sprint 05 - 2025 | Meera Nair | Medium | 3 | Done | 2025-03-05 | 2025-03-14 | 2025-03-16 | Operations | Medium | 14 | 18 | Scope Clarification | 2025-03-02 | 2025-03-15 | 10 | Yes | 1
APT-0126 | Customer Onboarding Automation | Sprint 08 - 2025 | Kabir Khan | High | 3 | Done | 2025-04-17 | 2025-04-25 | 2025-04-25 | Operations | Medium | 15 | 17 | None | 2025-04-13 | 2025-04-26 | 7 | No | 1
APT-0127 | API Reliability Upgrade | Sprint 12 - 2025 | Sara Thomas | Medium | 1 | To Do | 2025-06-12 | 2025-06-24 |  | Data Analytics | Low | 5 | 0 | Resource Constraint | 2025-06-08 | 2025-06-21 | 0 | Yes | 0
APT-0128 | Operations SLA Dashboard | Sprint 07 - 2025 | Rohan Gupta | Medium | 8 | Done | 2025-04-06 | 2025-04-13 | 2025-04-12 | QA | Low | 44 | 49 | None | 2025-03-30 | 2025-04-12 | 5 | No | 1
APT-0129 | Backlog Prioritization Framework | Sprint 12 - 2025 | Vikram Singh | High | 1 | Done | 2025-06-10 | 2025-06-15 | 2025-06-17 | Operations | Medium | 4 | 4 | UAT Feedback | 2025-06-08 | 2025-06-21 | 6 | Yes | 1
APT-0130 | Backlog Prioritization Framework | Sprint 09 - 2025 | Sara Thomas | Medium | 1 | To Do | 2025-04-30 | 2025-05-03 |  | Customer Success | High | 7 | 0 | Dependency Blocker | 2025-04-27 | 2025-05-10 | 0 | Yes | 0
APT-0131 | Data Quality Remediation | Sprint 01 - 2025 | Rohan Gupta | Low | 3 | In Progress | 2025-01-07 | 2025-01-19 |  | Product | Low | 10 | 5 | Scope Clarification | 2025-01-05 | 2025-01-18 | 0 | Yes | 0
APT-0132 | Backlog Prioritization Framework | Sprint 02 - 2025 | Aarav Mehta | Low | 3 | Done | 2025-01-22 | 2025-01-29 | 2025-01-29 | Customer Success | High | 15 | 18 | None | 2025-01-19 | 2025-02-01 | 6 | No | 1
APT-0133 | Data Quality Remediation | Sprint 02 - 2025 | Meera Nair | High | 13 | Done | 2025-01-27 | 2025-01-31 | 2025-02-01 | QA | High | 65 | 90 | Requirement Change | 2025-01-19 | 2025-02-01 | 4 | Yes | 1
APT-0134 | Operations SLA Dashboard | Sprint 11 - 2025 | Meera Nair | Critical | 5 | Testing | 2025-06-01 | 2025-06-08 |  | Engineering | High | 30 | 32 | Environment Issue | 2025-05-25 | 2025-06-07 | 0 | Yes | 0
APT-0135 | Mobile Experience Improvements | Sprint 11 - 2025 | Aarav Mehta | Critical | 3 | Done | 2025-05-27 | 2025-06-08 | 2025-06-11 | Product | Medium | 21 | 26 | Requirement Change | 2025-05-25 | 2025-06-07 | 14 | Yes | 1
APT-0136 | Mobile Experience Improvements | Sprint 05 - 2025 | Ananya Rao | Medium | 2 | Done | 2025-03-07 | 2025-03-11 | 2025-03-13 | Customer Success | Low | 8 | 6 | Scope Clarification | 2025-03-02 | 2025-03-15 | 5 | Yes | 1
APT-0137 | Sprint Reporting Hub | Sprint 12 - 2025 | Rohan Gupta | Medium | 3 | Done | 2025-06-09 | 2025-06-16 | 2025-06-16 | Customer Success | Low | 14 | 16 | None | 2025-06-08 | 2025-06-21 | 6 | No | 1
APT-0138 | Customer Onboarding Automation | Sprint 08 - 2025 | Isha Sharma | Medium | 2 | Done | 2025-04-20 | 2025-04-29 | 2025-04-29 | Customer Success | High | 15 | 22 | None | 2025-04-13 | 2025-04-26 | 8 | No | 1
APT-0139 | Customer Onboarding Automation | Sprint 11 - 2025 | Dev Patel | Medium | 3 | Done | 2025-05-30 | 2025-06-05 | 2025-06-04 | Product | Medium | 14 | 18 | None | 2025-05-25 | 2025-06-07 | 4 | No | 1
APT-0140 | Sprint Reporting Hub | Sprint 08 - 2025 | Aarav Mehta | High | 8 | Done | 2025-04-20 | 2025-05-01 | 2025-05-03 | Customer Success | Low | 44 | 48 | Dependency Blocker | 2025-04-13 | 2025-04-26 | 12 | Yes | 1
APT-0141 | Sprint Reporting Hub | Sprint 10 - 2025 | Dev Patel | Medium | 13 | Done | 2025-05-11 | 2025-05-22 | 2025-05-24 | Customer Success | High | 59 | 87 | Environment Issue | 2025-05-11 | 2025-05-24 | 12 | Yes | 1
APT-0142 | Stakeholder Notification Service | Sprint 07 - 2025 | Rohan Gupta | Medium | 8 | Done | 2025-03-31 | 2025-04-09 | 2025-04-09 | Data Analytics | Low | 44 | 49 | None | 2025-03-30 | 2025-04-12 | 8 | No | 1
APT-0143 | Sprint Reporting Hub | Sprint 04 - 2025 | Kabir Khan | Critical | 3 | Done | 2025-02-23 | 2025-02-27 | 2025-03-01 | Operations | Medium | 15 | 18 | Scope Clarification | 2025-02-16 | 2025-03-01 | 5 | Yes | 1
APT-0144 | Billing Workflow Optimization | Sprint 03 - 2025 | Sara Thomas | Medium | 1 | Done | 2025-02-04 | 2025-02-12 | 2025-02-12 | Data Analytics | Low | 4 | 5 | None | 2025-02-02 | 2025-02-15 | 7 | No | 1
APT-0145 | API Reliability Upgrade | Sprint 02 - 2025 | Rohan Gupta | High | 2 | Done | 2025-01-21 | 2025-01-29 | 2025-01-28 | QA | High | 12 | 18 | None | 2025-01-19 | 2025-02-01 | 6 | No | 1
APT-0146 | Customer Onboarding Automation | Sprint 02 - 2025 | Ananya Rao | Medium | 2 | Done | 2025-01-26 | 2025-02-06 | 2025-02-06 | Data Analytics | Medium | 10 | 12 | None | 2025-01-19 | 2025-02-01 | 10 | No | 1
APT-0147 | Mobile Experience Improvements | Sprint 10 - 2025 | Vikram Singh | Low | 2 | Done | 2025-05-19 | 2025-05-27 | 2025-05-28 | QA | Medium | 12 | 12 | Resource Constraint | 2025-05-11 | 2025-05-24 | 8 | Yes | 1
APT-0148 | Billing Workflow Optimization | Sprint 03 - 2025 | Vikram Singh | Medium | 3 | Testing | 2025-02-03 | 2025-02-15 |  | QA | Medium | 16 | 14 | Environment Issue | 2025-02-02 | 2025-02-15 | 0 | Yes | 0
APT-0149 | User Access Governance | Sprint 09 - 2025 | Zoya Fernandes | High | 5 | Done | 2025-05-04 | 2025-05-14 | 2025-05-13 | Data Analytics | Medium | 24 | 26 | None | 2025-04-27 | 2025-05-10 | 8 | No | 1
APT-0150 | Backlog Prioritization Framework | Sprint 08 - 2025 | Kabir Khan | Medium | 3 | Done | 2025-04-18 | 2025-04-25 | 2025-04-24 | Data Analytics | Medium | 13 | 14 | None | 2025-04-13 | 2025-04-26 | 5 | No | 1
APT-0151 | Operations SLA Dashboard | Sprint 03 - 2025 | Dev Patel | High | 3 | Done | 2025-02-04 | 2025-02-12 | 2025-02-12 | Customer Success | Low | 16 | 14 | None | 2025-02-02 | 2025-02-15 | 7 | No | 1
APT-0152 | Mobile Experience Improvements | Sprint 02 - 2025 | Dev Patel | Critical | 2 | Done | 2025-01-22 | 2025-01-29 | 2025-01-30 | Customer Success | Medium | 12 | 15 | Environment Issue | 2025-01-19 | 2025-02-01 | 7 | Yes | 1
APT-0153 | Operations SLA Dashboard | Sprint 10 - 2025 | Vikram Singh | Medium | 5 | Done | 2025-05-19 | 2025-05-24 | 2025-05-24 | Data Analytics | Low | 17 | 18 | None | 2025-05-11 | 2025-05-24 | 4 | No | 1
APT-0154 | Stakeholder Notification Service | Sprint 07 - 2025 | Zoya Fernandes | High | 5 | Done | 2025-04-03 | 2025-04-10 | 2025-04-10 | Customer Success | Low | 28 | 35 | None | 2025-03-30 | 2025-04-12 | 6 | No | 1
APT-0155 | Customer Onboarding Automation | Sprint 01 - 2025 | Neha Verma | High | 5 | To Do | 2025-01-13 | 2025-01-22 |  | Data Analytics | Low | 30 | 0 | Resource Constraint | 2025-01-05 | 2025-01-18 | 0 | Yes | 0
APT-0156 | User Access Governance | Sprint 06 - 2025 | Zoya Fernandes | Low | 5 | Done | 2025-03-19 | 2025-03-22 | 2025-03-24 | Product | Low | 21 | 20 | Resource Constraint | 2025-03-16 | 2025-03-29 | 4 | Yes | 1
APT-0157 | API Reliability Upgrade | Sprint 02 - 2025 | Aarav Mehta | Low | 1 | Done | 2025-01-20 | 2025-01-23 | 2025-01-24 | Product | High | 6 | 8 | Dependency Blocker | 2025-01-19 | 2025-02-01 | 3 | Yes | 1
APT-0158 | Stakeholder Notification Service | Sprint 10 - 2025 | Arjun Menon | Medium | 1 | Done | 2025-05-11 | 2025-05-19 | 2025-05-22 | Product | Medium | 6 | 8 | Environment Issue | 2025-05-11 | 2025-05-24 | 10 | Yes | 1
APT-0159 | API Reliability Upgrade | Sprint 02 - 2025 | Kabir Khan | Low | 13 | Testing | 2025-01-21 | 2025-01-29 |  | Operations | Low | 41 | 35 | Resource Constraint | 2025-01-19 | 2025-02-01 | 0 | Yes | 0
APT-0160 | Stakeholder Notification Service | Sprint 08 - 2025 | Rohan Gupta | Medium | 3 | Done | 2025-04-13 | 2025-04-21 | 2025-04-23 | Data Analytics | Low | 14 | 16 | Dependency Blocker | 2025-04-13 | 2025-04-26 | 9 | Yes | 1
APT-0161 | Stakeholder Notification Service | Sprint 01 - 2025 | Sara Thomas | High | 5 | Done | 2025-01-07 | 2025-01-16 | 2025-01-16 | Engineering | Low | 29 | 30 | None | 2025-01-05 | 2025-01-18 | 8 | No | 1
APT-0162 | Data Quality Remediation | Sprint 04 - 2025 | Sara Thomas | High | 13 | Done | 2025-02-20 | 2025-02-27 | 2025-02-28 | Product | Low | 46 | 44 | Resource Constraint | 2025-02-16 | 2025-03-01 | 7 | Yes | 1
APT-0163 | Customer Onboarding Automation | Sprint 10 - 2025 | Ananya Rao | Medium | 3 | Done | 2025-05-16 | 2025-05-25 | 2025-05-24 | Product | Low | 15 | 16 | None | 2025-05-11 | 2025-05-24 | 7 | No | 1
APT-0164 | Stakeholder Notification Service | Sprint 10 - 2025 | Rohan Gupta | Medium | 5 | Done | 2025-05-18 | 2025-05-27 | 2025-05-26 | Operations | Low | 22 | 19 | None | 2025-05-11 | 2025-05-24 | 7 | No | 1
APT-0165 | Billing Workflow Optimization | Sprint 05 - 2025 | Zoya Fernandes | Low | 2 | Done | 2025-03-09 | 2025-03-18 | 2025-03-17 | Data Analytics | Medium | 10 | 9 | None | 2025-03-02 | 2025-03-15 | 7 | No | 1
APT-0166 | Stakeholder Notification Service | Sprint 08 - 2025 | Arjun Menon | Critical | 2 | Done | 2025-04-21 | 2025-05-01 | 2025-05-01 | Engineering | Low | 13 | 15 | None | 2025-04-13 | 2025-04-26 | 9 | No | 1
APT-0167 | Sprint Reporting Hub | Sprint 11 - 2025 | Zoya Fernandes | High | 1 | Done | 2025-06-02 | 2025-06-06 | 2025-06-06 | QA | Medium | 7 | 8 | None | 2025-05-25 | 2025-06-07 | 3 | No | 1
APT-0168 | Billing Workflow Optimization | Sprint 05 - 2025 | Ananya Rao | Low | 5 | Done | 2025-03-09 | 2025-03-20 | 2025-03-21 | Product | Low | 16 | 16 | Environment Issue | 2025-03-02 | 2025-03-15 | 11 | Yes | 1
APT-0169 | Mobile Experience Improvements | Sprint 04 - 2025 | Ananya Rao | Low | 5 | In Progress | 2025-02-23 | 2025-03-05 |  | Product | Low | 22 | 12 | Scope Clarification | 2025-02-16 | 2025-03-01 | 0 | Yes | 0
APT-0170 | Mobile Experience Improvements | Sprint 08 - 2025 | Kabir Khan | Medium | 8 | Done | 2025-04-17 | 2025-04-21 | 2025-04-21 | Customer Success | Low | 36 | 36 | None | 2025-04-13 | 2025-04-26 | 3 | No | 1
APT-0171 | Operations SLA Dashboard | Sprint 05 - 2025 | Aarav Mehta | High | 2 | Done | 2025-03-08 | 2025-03-20 | 2025-03-20 | QA | Low | 12 | 10 | None | 2025-03-02 | 2025-03-15 | 11 | No | 1
APT-0172 | Backlog Prioritization Framework | Sprint 06 - 2025 | Isha Sharma | Medium | 3 | Done | 2025-03-23 | 2025-03-31 | 2025-03-30 | Product | Low | 11 | 9 | None | 2025-03-16 | 2025-03-29 | 6 | No | 1
APT-0173 | Operations SLA Dashboard | Sprint 12 - 2025 | Kabir Khan | Medium | 5 | In Progress | 2025-06-08 | 2025-06-20 |  | Product | Low | 16 | 8 | Resource Constraint | 2025-06-08 | 2025-06-21 | 0 | Yes | 0
APT-0174 | Stakeholder Notification Service | Sprint 06 - 2025 | Dev Patel | Medium | 3 | Done | 2025-03-16 | 2025-03-23 | 2025-03-24 | Customer Success | Medium | 12 | 15 | Requirement Change | 2025-03-16 | 2025-03-29 | 7 | Yes | 1
APT-0175 | API Reliability Upgrade | Sprint 06 - 2025 | Zoya Fernandes | Low | 2 | Done | 2025-03-23 | 2025-03-27 | 2025-03-27 | Product | Medium | 9 | 9 | None | 2025-03-16 | 2025-03-29 | 3 | No | 1
APT-0176 | API Reliability Upgrade | Sprint 04 - 2025 | Sara Thomas | Low | 2 | Done | 2025-02-19 | 2025-02-26 | 2025-02-28 | Customer Success | Medium | 9 | 9 | UAT Feedback | 2025-02-16 | 2025-03-01 | 8 | Yes | 1
APT-0177 | Mobile Experience Improvements | Sprint 11 - 2025 | Sara Thomas | Low | 8 | Done | 2025-05-28 | 2025-06-05 | 2025-06-05 | Data Analytics | Low | 28 | 25 | None | 2025-05-25 | 2025-06-07 | 7 | No | 1
APT-0178 | Customer Onboarding Automation | Sprint 10 - 2025 | Meera Nair | Medium | 3 | Testing | 2025-05-16 | 2025-05-25 |  | Engineering | Medium | 15 | 15 | Requirement Change | 2025-05-11 | 2025-05-24 | 0 | Yes | 0
APT-0179 | Billing Workflow Optimization | Sprint 07 - 2025 | Aarav Mehta | Low | 3 | In Progress | 2025-04-06 | 2025-04-09 |  | Operations | High | 20 | 14 | Requirement Change | 2025-03-30 | 2025-04-12 | 0 | Yes | 0
APT-0180 | Customer Onboarding Automation | Sprint 01 - 2025 | Zoya Fernandes | Medium | 2 | Done | 2025-01-05 | 2025-01-14 | 2025-01-16 | Product | Medium | 8 | 10 | Environment Issue | 2025-01-05 | 2025-01-18 | 10 | Yes | 1
APT-0181 | Sprint Reporting Hub | Sprint 09 - 2025 | Ananya Rao | Low | 1 | Done | 2025-04-27 | 2025-05-09 | 2025-05-09 | Data Analytics | Medium | 5 | 6 | None | 2025-04-27 | 2025-05-10 | 11 | No | 1
APT-0182 | Backlog Prioritization Framework | Sprint 11 - 2025 | Dev Patel | Medium | 5 | Done | 2025-05-27 | 2025-06-04 | 2025-06-04 | Operations | High | 21 | 23 | None | 2025-05-25 | 2025-06-07 | 7 | No | 1
APT-0183 | User Access Governance | Sprint 02 - 2025 | Meera Nair | Low | 1 | Done | 2025-01-24 | 2025-01-29 | 2025-01-30 | Operations | Medium | 6 | 7 | Scope Clarification | 2025-01-19 | 2025-02-01 | 5 | Yes | 1
APT-0184 | Customer Onboarding Automation | Sprint 02 - 2025 | Meera Nair | Medium | 2 | Done | 2025-01-20 | 2025-01-29 | 2025-01-29 | Operations | High | 11 | 17 | None | 2025-01-19 | 2025-02-01 | 8 | No | 1
APT-0185 | Mobile Experience Improvements | Sprint 04 - 2025 | Ananya Rao | High | 3 | Done | 2025-02-16 | 2025-02-23 | 2025-02-21 | QA | Medium | 21 | 23 | None | 2025-02-16 | 2025-03-01 | 4 | No | 1
APT-0186 | Backlog Prioritization Framework | Sprint 11 - 2025 | Zoya Fernandes | Medium | 1 | In Progress | 2025-06-02 | 2025-06-07 |  | Customer Success | Low | 4 | 2 | UAT Feedback | 2025-05-25 | 2025-06-07 | 0 | Yes | 0
APT-0187 | Backlog Prioritization Framework | Sprint 02 - 2025 | Sara Thomas | Medium | 3 | Done | 2025-01-25 | 2025-01-29 | 2025-01-29 | Product | High | 21 | 30 | None | 2025-01-19 | 2025-02-01 | 3 | No | 1
APT-0188 | Billing Workflow Optimization | Sprint 04 - 2025 | Kabir Khan | High | 3 | Done | 2025-02-23 | 2025-02-26 | 2025-02-27 | Engineering | Medium | 17 | 20 | Environment Issue | 2025-02-16 | 2025-03-01 | 3 | Yes | 1
APT-0189 | Stakeholder Notification Service | Sprint 01 - 2025 | Aarav Mehta | Medium | 5 | Done | 2025-01-06 | 2025-01-17 | 2025-01-19 | Product | Low | 19 | 17 | Environment Issue | 2025-01-05 | 2025-01-18 | 12 | Yes | 1
APT-0190 | User Access Governance | Sprint 10 - 2025 | Aarav Mehta | Low | 3 | Done | 2025-05-18 | 2025-05-26 | 2025-05-27 | Product | High | 20 | 23 | Requirement Change | 2025-05-11 | 2025-05-24 | 8 | Yes | 1
APT-0191 | Mobile Experience Improvements | Sprint 12 - 2025 | Aarav Mehta | High | 5 | To Do | 2025-06-09 | 2025-06-18 |  | Data Analytics | High | 41 | 0 | Requirement Change | 2025-06-08 | 2025-06-21 | 0 | Yes | 0
APT-0192 | Operations SLA Dashboard | Sprint 05 - 2025 | Zoya Fernandes | Medium | 5 | To Do | 2025-03-10 | 2025-03-20 |  | Engineering | Low | 19 | 0 | Requirement Change | 2025-03-02 | 2025-03-15 | 0 | Yes | 0
APT-0193 | Sprint Reporting Hub | Sprint 05 - 2025 | Rohan Gupta | Medium | 5 | Done | 2025-03-07 | 2025-03-11 | 2025-03-12 | Operations | Medium | 24 | 27 | Dependency Blocker | 2025-03-02 | 2025-03-15 | 4 | Yes | 1
APT-0194 | API Reliability Upgrade | Sprint 06 - 2025 | Neha Verma | Medium | 5 | Testing | 2025-03-20 | 2025-03-30 |  | Engineering | Low | 19 | 18 | Environment Issue | 2025-03-16 | 2025-03-29 | 0 | Yes | 0
APT-0195 | Mobile Experience Improvements | Sprint 09 - 2025 | Aarav Mehta | High | 2 | Done | 2025-04-27 | 2025-05-09 | 2025-05-11 | QA | High | 16 | 17 | Resource Constraint | 2025-04-27 | 2025-05-10 | 13 | Yes | 1
APT-0196 | Operations SLA Dashboard | Sprint 01 - 2025 | Sara Thomas | High | 1 | Done | 2025-01-10 | 2025-01-20 | 2025-01-20 | Product | Medium | 6 | 6 | None | 2025-01-05 | 2025-01-18 | 9 | No | 1
APT-0197 | API Reliability Upgrade | Sprint 12 - 2025 | Ananya Rao | Medium | 5 | In Progress | 2025-06-10 | 2025-06-19 |  | Customer Success | High | 37 | 25 | Requirement Change | 2025-06-08 | 2025-06-21 | 0 | Yes | 0
APT-0198 | Stakeholder Notification Service | Sprint 08 - 2025 | Vikram Singh | Medium | 1 | Done | 2025-04-21 | 2025-04-28 | 2025-04-30 | Operations | Low | 5 | 6 | Scope Clarification | 2025-04-13 | 2025-04-26 | 8 | Yes | 1
APT-0199 | Mobile Experience Improvements | Sprint 10 - 2025 | Arjun Menon | Medium | 5 | Done | 2025-05-15 | 2025-05-18 | 2025-05-18 | Customer Success | Low | 28 | 34 | None | 2025-05-11 | 2025-05-24 | 2 | No | 1
APT-0200 | Billing Workflow Optimization | Sprint 07 - 2025 | Ananya Rao | Critical | 8 | In Progress | 2025-03-30 | 2025-04-03 |  | QA | Low | 52 | 40 | Resource Constraint | 2025-03-30 | 2025-04-12 | 0 | Yes | 0
APT-0201 | Stakeholder Notification Service | Sprint 11 - 2025 | Zoya Fernandes | Medium | 2 | In Progress | 2025-06-01 | 2025-06-10 |  | Operations | Low | 10 | 4 | UAT Feedback | 2025-05-25 | 2025-06-07 | 0 | Yes | 0
APT-0202 | Stakeholder Notification Service | Sprint 12 - 2025 | Zoya Fernandes | Medium | 8 | Done | 2025-06-09 | 2025-06-17 | 2025-06-17 | Customer Success | Low | 30 | 31 | None | 2025-06-08 | 2025-06-21 | 7 | No | 1
APT-0203 | Data Quality Remediation | Sprint 01 - 2025 | Aarav Mehta | High | 3 | Testing | 2025-01-05 | 2025-01-14 |  | Customer Success | Medium | 15 | 17 | Environment Issue | 2025-01-05 | 2025-01-18 | 0 | Yes | 0
APT-0204 | User Access Governance | Sprint 11 - 2025 | Aarav Mehta | High | 5 | In Progress | 2025-06-02 | 2025-06-12 |  | Data Analytics | Low | 23 | 14 | Dependency Blocker | 2025-05-25 | 2025-06-07 | 0 | Yes | 0
APT-0205 | Data Quality Remediation | Sprint 09 - 2025 | Kabir Khan | Low | 8 | Testing | 2025-04-30 | 2025-05-04 |  | Engineering | Low | 34 | 34 | UAT Feedback | 2025-04-27 | 2025-05-10 | 0 | Yes | 0
APT-0206 | Stakeholder Notification Service | Sprint 07 - 2025 | Sara Thomas | Critical | 5 | Done | 2025-03-31 | 2025-04-11 | 2025-04-11 | Operations | Medium | 35 | 45 | None | 2025-03-30 | 2025-04-12 | 10 | No | 1
APT-0207 | Customer Onboarding Automation | Sprint 10 - 2025 | Aarav Mehta | Medium | 2 | To Do | 2025-05-17 | 2025-05-21 |  | Operations | Medium | 11 | 0 | Resource Constraint | 2025-05-11 | 2025-05-24 | 0 | Yes | 0
APT-0208 | Data Quality Remediation | Sprint 09 - 2025 | Rohan Gupta | High | 1 | Done | 2025-04-29 | 2025-05-06 | 2025-05-09 | Product | Medium | 5 | 5 | Scope Clarification | 2025-04-27 | 2025-05-10 | 9 | Yes | 1
APT-0209 | Mobile Experience Improvements | Sprint 01 - 2025 | Vikram Singh | Critical | 13 | Done | 2025-01-09 | 2025-01-19 | 2025-01-19 | Data Analytics | High | 69 | 94 | None | 2025-01-05 | 2025-01-18 | 9 | No | 1
APT-0210 | Data Quality Remediation | Sprint 10 - 2025 | Meera Nair | Medium | 5 | Done | 2025-05-12 | 2025-05-22 | 2025-05-22 | Customer Success | Medium | 31 | 37 | None | 2025-05-11 | 2025-05-24 | 9 | No | 1
APT-0211 | Stakeholder Notification Service | Sprint 08 - 2025 | Zoya Fernandes | Critical | 3 | Done | 2025-04-16 | 2025-04-26 | 2025-04-25 | Product | High | 17 | 25 | None | 2025-04-13 | 2025-04-26 | 8 | No | 1
APT-0212 | Mobile Experience Improvements | Sprint 06 - 2025 | Meera Nair | Medium | 3 | Done | 2025-03-23 | 2025-03-28 | 2025-03-26 | QA | Medium | 19 | 25 | None | 2025-03-16 | 2025-03-29 | 2 | No | 1
APT-0213 | Operations SLA Dashboard | Sprint 03 - 2025 | Neha Verma | Critical | 5 | To Do | 2025-02-07 | 2025-02-16 |  | Customer Success | Low | 33 | 0 | Dependency Blocker | 2025-02-02 | 2025-02-15 | 0 | Yes | 0
APT-0214 | API Reliability Upgrade | Sprint 09 - 2025 | Zoya Fernandes | High | 8 | Testing | 2025-05-04 | 2025-05-11 |  | Operations | Medium | 45 | 43 | Resource Constraint | 2025-04-27 | 2025-05-10 | 0 | Yes | 0
APT-0215 | Backlog Prioritization Framework | Sprint 08 - 2025 | Rohan Gupta | Medium | 5 | Done | 2025-04-14 | 2025-04-26 | 2025-04-25 | Data Analytics | Medium | 22 | 25 | None | 2025-04-13 | 2025-04-26 | 10 | No | 1
APT-0216 | Backlog Prioritization Framework | Sprint 10 - 2025 | Arjun Menon | Critical | 13 | Done | 2025-05-15 | 2025-05-19 | 2025-05-17 | Engineering | High | 89 | 108 | None | 2025-05-11 | 2025-05-24 | 1 | No | 1
APT-0217 | Mobile Experience Improvements | Sprint 11 - 2025 | Rohan Gupta | Low | 5 | Done | 2025-05-29 | 2025-06-01 | 2025-05-31 | Engineering | Low | 17 | 17 | None | 2025-05-25 | 2025-06-07 | 1 | No | 1
APT-0218 | Sprint Reporting Hub | Sprint 12 - 2025 | Kabir Khan | High | 3 | Done | 2025-06-11 | 2025-06-18 | 2025-06-19 | Engineering | Low | 19 | 19 | Dependency Blocker | 2025-06-08 | 2025-06-21 | 7 | Yes | 1
APT-0219 | Operations SLA Dashboard | Sprint 08 - 2025 | Arjun Menon | High | 1 | Done | 2025-04-21 | 2025-04-24 | 2025-04-24 | Product | Medium | 5 | 5 | None | 2025-04-13 | 2025-04-26 | 2 | No | 1
APT-0220 | Customer Onboarding Automation | Sprint 10 - 2025 | Arjun Menon | Medium | 8 | In Progress | 2025-05-13 | 2025-05-23 |  | Operations | High | 58 | 36 | Environment Issue | 2025-05-11 | 2025-05-24 | 0 | Yes | 0
APT-0221 | Customer Onboarding Automation | Sprint 05 - 2025 | Dev Patel | High | 5 | Done | 2025-03-02 | 2025-03-09 | 2025-03-11 | Customer Success | High | 37 | 39 | Requirement Change | 2025-03-02 | 2025-03-15 | 8 | Yes | 1
APT-0222 | Backlog Prioritization Framework | Sprint 07 - 2025 | Rohan Gupta | High | 2 | Done | 2025-03-30 | 2025-04-11 | 2025-04-12 | Product | Low | 7 | 8 | UAT Feedback | 2025-03-30 | 2025-04-12 | 12 | Yes | 1
APT-0223 | Backlog Prioritization Framework | Sprint 09 - 2025 | Vikram Singh | High | 3 | Done | 2025-05-03 | 2025-05-08 | 2025-05-09 | Data Analytics | Low | 14 | 13 | UAT Feedback | 2025-04-27 | 2025-05-10 | 5 | Yes | 1
APT-0224 | User Access Governance | Sprint 06 - 2025 | Rohan Gupta | Medium | 8 | Done | 2025-03-18 | 2025-03-26 | 2025-03-26 | Engineering | High | 43 | 48 | None | 2025-03-16 | 2025-03-29 | 7 | No | 1
APT-0225 | Mobile Experience Improvements | Sprint 11 - 2025 | Dev Patel | Medium | 3 | Done | 2025-05-26 | 2025-06-02 | 2025-06-02 | Engineering | Medium | 12 | 15 | None | 2025-05-25 | 2025-06-07 | 6 | No | 1
APT-0226 | Customer Onboarding Automation | Sprint 01 - 2025 | Sara Thomas | Low | 3 | To Do | 2025-01-05 | 2025-01-17 |  | Product | Low | 10 | 0 | Resource Constraint | 2025-01-05 | 2025-01-18 | 0 | Yes | 0
APT-0227 | Mobile Experience Improvements | Sprint 05 - 2025 | Arjun Menon | High | 2 | Done | 2025-03-08 | 2025-03-18 | 2025-03-19 | Engineering | Low | 9 | 10 | UAT Feedback | 2025-03-02 | 2025-03-15 | 10 | Yes | 1
APT-0228 | Stakeholder Notification Service | Sprint 11 - 2025 | Arjun Menon | High | 3 | Done | 2025-05-28 | 2025-06-03 | 2025-06-02 | Data Analytics | High | 21 | 28 | None | 2025-05-25 | 2025-06-07 | 4 | No | 1
APT-0229 | Data Quality Remediation | Sprint 03 - 2025 | Isha Sharma | Low | 2 | Done | 2025-02-07 | 2025-02-17 | 2025-02-17 | Customer Success | Low | 11 | 11 | None | 2025-02-02 | 2025-02-15 | 9 | No | 1
APT-0230 | User Access Governance | Sprint 09 - 2025 | Sara Thomas | High | 5 | Done | 2025-04-28 | 2025-05-10 | 2025-05-10 | QA | Low | 22 | 27 | None | 2025-04-27 | 2025-05-10 | 11 | No | 1
APT-0231 | Mobile Experience Improvements | Sprint 03 - 2025 | Isha Sharma | Critical | 8 | Done | 2025-02-02 | 2025-02-12 | 2025-02-12 | Product | Medium | 64 | 84 | None | 2025-02-02 | 2025-02-15 | 9 | No | 1
APT-0232 | Sprint Reporting Hub | Sprint 08 - 2025 | Arjun Menon | Medium | 1 | Done | 2025-04-14 | 2025-04-20 | 2025-04-20 | Operations | High | 5 | 5 | None | 2025-04-13 | 2025-04-26 | 5 | No | 1
APT-0233 | Billing Workflow Optimization | Sprint 06 - 2025 | Aarav Mehta | High | 3 | Done | 2025-03-19 | 2025-03-22 | 2025-03-24 | QA | Medium | 13 | 16 | Requirement Change | 2025-03-16 | 2025-03-29 | 4 | Yes | 1
APT-0234 | User Access Governance | Sprint 09 - 2025 | Kabir Khan | High | 1 | To Do | 2025-04-30 | 2025-05-07 |  | Engineering | High | 7 | 0 | Requirement Change | 2025-04-27 | 2025-05-10 | 0 | Yes | 0
APT-0235 | Sprint Reporting Hub | Sprint 10 - 2025 | Vikram Singh | Medium | 8 | Done | 2025-05-15 | 2025-05-27 | 2025-05-28 | Data Analytics | Low | 41 | 35 | Environment Issue | 2025-05-11 | 2025-05-24 | 12 | Yes | 1
APT-0236 | Mobile Experience Improvements | Sprint 06 - 2025 | Neha Verma | Medium | 3 | Done | 2025-03-23 | 2025-03-31 | 2025-03-29 | Data Analytics | Medium | 14 | 16 | None | 2025-03-16 | 2025-03-29 | 5 | No | 1
APT-0237 | Stakeholder Notification Service | Sprint 10 - 2025 | Meera Nair | Low | 2 | Done | 2025-05-16 | 2025-05-26 | 2025-05-27 | Product | Medium | 9 | 8 | Resource Constraint | 2025-05-11 | 2025-05-24 | 10 | Yes | 1
APT-0238 | Backlog Prioritization Framework | Sprint 01 - 2025 | Ananya Rao | Medium | 3 | Done | 2025-01-13 | 2025-01-20 | 2025-01-21 | QA | Low | 14 | 17 | Dependency Blocker | 2025-01-05 | 2025-01-18 | 7 | Yes | 1
APT-0239 | User Access Governance | Sprint 01 - 2025 | Arjun Menon | Medium | 13 | Done | 2025-01-10 | 2025-01-17 | 2025-01-17 | Customer Success | Low | 74 | 71 | None | 2025-01-05 | 2025-01-18 | 6 | No | 1
APT-0240 | API Reliability Upgrade | Sprint 10 - 2025 | Dev Patel | Medium | 5 | Testing | 2025-05-18 | 2025-05-29 |  | Engineering | Medium | 22 | 21 | Dependency Blocker | 2025-05-11 | 2025-05-24 | 0 | Yes | 0
APT-0241 | User Access Governance | Sprint 04 - 2025 | Meera Nair | High | 3 | Testing | 2025-02-20 | 2025-03-03 |  | Engineering | High | 20 | 25 | Resource Constraint | 2025-02-16 | 2025-03-01 | 0 | Yes | 0
APT-0242 | Mobile Experience Improvements | Sprint 06 - 2025 | Sara Thomas | Medium | 1 | Done | 2025-03-17 | 2025-03-26 | 2025-03-28 | QA | Low | 4 | 4 | Requirement Change | 2025-03-16 | 2025-03-29 | 10 | Yes | 1
APT-0243 | Billing Workflow Optimization | Sprint 07 - 2025 | Arjun Menon | Medium | 1 | Done | 2025-04-07 | 2025-04-13 | 2025-04-13 | Customer Success | Low | 6 | 6 | None | 2025-03-30 | 2025-04-12 | 5 | No | 1
APT-0244 | Backlog Prioritization Framework | Sprint 10 - 2025 | Ananya Rao | High | 3 | Done | 2025-05-11 | 2025-05-21 | 2025-05-21 | Engineering | Low | 15 | 17 | None | 2025-05-11 | 2025-05-24 | 9 | No | 1
APT-0245 | User Access Governance | Sprint 02 - 2025 | Isha Sharma | Medium | 8 | Done | 2025-01-27 | 2025-02-01 | 2025-02-03 | Engineering | Medium | 39 | 44 | UAT Feedback | 2025-01-19 | 2025-02-01 | 6 | Yes | 1
APT-0246 | Stakeholder Notification Service | Sprint 04 - 2025 | Vikram Singh | Medium | 8 | Testing | 2025-02-19 | 2025-02-22 |  | Customer Success | Low | 28 | 22 | Dependency Blocker | 2025-02-16 | 2025-03-01 | 0 | Yes | 0
APT-0247 | Data Quality Remediation | Sprint 01 - 2025 | Dev Patel | Medium | 8 | Done | 2025-01-12 | 2025-01-21 | 2025-01-22 | Customer Success | Low | 45 | 42 | Environment Issue | 2025-01-05 | 2025-01-18 | 9 | Yes | 1
APT-0248 | API Reliability Upgrade | Sprint 01 - 2025 | Dev Patel | High | 8 | Done | 2025-01-11 | 2025-01-19 | 2025-01-21 | Product | Medium | 43 | 44 | Resource Constraint | 2025-01-05 | 2025-01-18 | 9 | Yes | 1
APT-0249 | Billing Workflow Optimization | Sprint 02 - 2025 | Rohan Gupta | High | 8 | Done | 2025-01-22 | 2025-01-30 | 2025-01-31 | Engineering | Low | 43 | 53 | Scope Clarification | 2025-01-19 | 2025-02-01 | 8 | Yes | 1
APT-0250 | Customer Onboarding Automation | Sprint 11 - 2025 | Isha Sharma | High | 3 | In Progress | 2025-05-28 | 2025-06-03 |  | Product | High | 19 | 17 | Environment Issue | 2025-05-25 | 2025-06-07 | 0 | Yes | 0
APT-0251 | Customer Onboarding Automation | Sprint 12 - 2025 | Dev Patel | Medium | 1 | Testing | 2025-06-11 | 2025-06-15 |  | Data Analytics | High | 7 | 7 | UAT Feedback | 2025-06-08 | 2025-06-21 | 0 | Yes | 0
APT-0252 | Customer Onboarding Automation | Sprint 09 - 2025 | Meera Nair | Medium | 8 | Done | 2025-04-29 | 2025-05-09 | 2025-05-09 | Customer Success | Low | 31 | 30 | None | 2025-04-27 | 2025-05-10 | 9 | No | 1
APT-0253 | Mobile Experience Improvements | Sprint 06 - 2025 | Isha Sharma | Low | 1 | Done | 2025-03-24 | 2025-03-31 | 2025-03-31 | Operations | Low | 5 | 6 | None | 2025-03-16 | 2025-03-29 | 6 | No | 1
APT-0254 | Stakeholder Notification Service | Sprint 02 - 2025 | Meera Nair | Critical | 8 | Done | 2025-01-25 | 2025-02-04 | 2025-02-03 | Customer Success | Low | 38 | 36 | None | 2025-01-19 | 2025-02-01 | 8 | No | 1
APT-0255 | Customer Onboarding Automation | Sprint 02 - 2025 | Ananya Rao | High | 5 | To Do | 2025-01-21 | 2025-01-27 |  | Operations | Low | 28 | 0 | UAT Feedback | 2025-01-19 | 2025-02-01 | 0 | Yes | 0
APT-0256 | Sprint Reporting Hub | Sprint 06 - 2025 | Isha Sharma | Medium | 3 | In Progress | 2025-03-16 | 2025-03-28 |  | Operations | Low | 14 | 10 | Environment Issue | 2025-03-16 | 2025-03-29 | 0 | Yes | 0
APT-0257 | Mobile Experience Improvements | Sprint 10 - 2025 | Arjun Menon | High | 5 | Done | 2025-05-14 | 2025-05-25 | 2025-05-25 | Customer Success | Low | 26 | 27 | None | 2025-05-11 | 2025-05-24 | 10 | No | 1
APT-0258 | Mobile Experience Improvements | Sprint 12 - 2025 | Zoya Fernandes | Medium | 1 | In Progress | 2025-06-13 | 2025-06-23 |  | Data Analytics | High | 6 | 3 | UAT Feedback | 2025-06-08 | 2025-06-21 | 0 | Yes | 0
APT-0259 | Stakeholder Notification Service | Sprint 10 - 2025 | Zoya Fernandes | Low | 2 | Done | 2025-05-18 | 2025-05-28 | 2025-05-28 | Operations | High | 9 | 12 | None | 2025-05-11 | 2025-05-24 | 9 | No | 1
APT-0260 | Stakeholder Notification Service | Sprint 08 - 2025 | Arjun Menon | High | 5 | In Progress | 2025-04-16 | 2025-04-27 |  | Customer Success | High | 25 | 15 | Dependency Blocker | 2025-04-13 | 2025-04-26 | 0 | Yes | 0
APT-0261 | Operations SLA Dashboard | Sprint 07 - 2025 | Isha Sharma | Medium | 3 | Done | 2025-03-31 | 2025-04-10 | 2025-04-08 | Operations | High | 18 | 26 | None | 2025-03-30 | 2025-04-12 | 7 | No | 1
APT-0262 | Operations SLA Dashboard | Sprint 06 - 2025 | Neha Verma | Low | 3 | Done | 2025-03-19 | 2025-03-28 | 2025-03-27 | Operations | Medium | 17 | 16 | None | 2025-03-16 | 2025-03-29 | 7 | No | 1
APT-0263 | Operations SLA Dashboard | Sprint 04 - 2025 | Meera Nair | Medium | 5 | Done | 2025-02-17 | 2025-02-23 | 2025-02-23 | Operations | Low | 19 | 18 | None | 2025-02-16 | 2025-03-01 | 5 | No | 1
APT-0264 | Billing Workflow Optimization | Sprint 01 - 2025 | Meera Nair | High | 5 | Done | 2025-01-10 | 2025-01-20 | 2025-01-21 | Customer Success | Low | 23 | 26 | Environment Issue | 2025-01-05 | 2025-01-18 | 10 | Yes | 1
APT-0265 | User Access Governance | Sprint 12 - 2025 | Vikram Singh | Medium | 3 | Done | 2025-06-16 | 2025-06-22 | 2025-06-24 | Customer Success | Low | 15 | 13 | Environment Issue | 2025-06-08 | 2025-06-21 | 7 | Yes | 1
APT-0266 | API Reliability Upgrade | Sprint 07 - 2025 | Arjun Menon | Low | 1 | Done | 2025-04-07 | 2025-04-17 | 2025-04-17 | Data Analytics | Medium | 4 | 4 | None | 2025-03-30 | 2025-04-12 | 9 | No | 1
APT-0267 | Sprint Reporting Hub | Sprint 08 - 2025 | Neha Verma | Medium | 13 | Done | 2025-04-17 | 2025-04-27 | 2025-04-27 | Operations | High | 94 | 124 | None | 2025-04-13 | 2025-04-26 | 9 | No | 1
APT-0268 | Data Quality Remediation | Sprint 06 - 2025 | Aarav Mehta | Medium | 8 | Done | 2025-03-18 | 2025-03-27 | 2025-03-27 | Operations | Low | 45 | 44 | None | 2025-03-16 | 2025-03-29 | 8 | No | 1
APT-0269 | Sprint Reporting Hub | Sprint 03 - 2025 | Vikram Singh | Medium | 5 | In Progress | 2025-02-04 | 2025-02-14 |  | Data Analytics | Low | 17 | 10 | Scope Clarification | 2025-02-02 | 2025-02-15 | 0 | Yes | 0
APT-0270 | Billing Workflow Optimization | Sprint 09 - 2025 | Arjun Menon | High | 3 | Done | 2025-04-27 | 2025-05-09 | 2025-05-11 | Operations | Low | 13 | 12 | Dependency Blocker | 2025-04-27 | 2025-05-10 | 13 | Yes | 1
APT-0271 | User Access Governance | Sprint 12 - 2025 | Meera Nair | Medium | 1 | Done | 2025-06-15 | 2025-06-25 | 2025-06-25 | Engineering | Medium | 5 | 6 | None | 2025-06-08 | 2025-06-21 | 9 | No | 1
APT-0272 | Mobile Experience Improvements | Sprint 11 - 2025 | Neha Verma | Medium | 5 | Done | 2025-05-30 | 2025-06-06 | 2025-06-08 | Operations | Low | 24 | 27 | Dependency Blocker | 2025-05-25 | 2025-06-07 | 8 | Yes | 1
APT-0273 | Operations SLA Dashboard | Sprint 07 - 2025 | Aarav Mehta | Medium | 5 | Done | 2025-03-30 | 2025-04-10 | 2025-04-12 | QA | High | 24 | 34 | Requirement Change | 2025-03-30 | 2025-04-12 | 12 | Yes | 1
APT-0274 | Operations SLA Dashboard | Sprint 10 - 2025 | Aarav Mehta | Medium | 5 | Done | 2025-05-14 | 2025-05-25 | 2025-05-26 | Data Analytics | Low | 19 | 22 | Scope Clarification | 2025-05-11 | 2025-05-24 | 11 | Yes | 1
APT-0275 | Backlog Prioritization Framework | Sprint 03 - 2025 | Meera Nair | High | 3 | Done | 2025-02-08 | 2025-02-11 | 2025-02-12 | QA | Low | 16 | 17 | UAT Feedback | 2025-02-02 | 2025-02-15 | 3 | Yes | 1
APT-0276 | API Reliability Upgrade | Sprint 10 - 2025 | Neha Verma | High | 5 | To Do | 2025-05-18 | 2025-05-29 |  | Engineering | Medium | 30 | 0 | Environment Issue | 2025-05-11 | 2025-05-24 | 0 | Yes | 0
APT-0277 | Stakeholder Notification Service | Sprint 09 - 2025 | Kabir Khan | Medium | 2 | Done | 2025-05-05 | 2025-05-13 | 2025-05-12 | Data Analytics | High | 12 | 16 | None | 2025-04-27 | 2025-05-10 | 6 | No | 1
APT-0278 | API Reliability Upgrade | Sprint 06 - 2025 | Ananya Rao | Medium | 1 | In Progress | 2025-03-20 | 2025-03-27 |  | Engineering | High | 7 | 4 | Environment Issue | 2025-03-16 | 2025-03-29 | 0 | Yes | 0
APT-0279 | User Access Governance | Sprint 04 - 2025 | Isha Sharma | Medium | 13 | Done | 2025-02-17 | 2025-02-26 | 2025-02-28 | QA | Low | 64 | 68 | Resource Constraint | 2025-02-16 | 2025-03-01 | 10 | Yes | 1
APT-0280 | Sprint Reporting Hub | Sprint 09 - 2025 | Kabir Khan | Medium | 8 | Testing | 2025-04-27 | 2025-05-01 |  | Product | Medium | 39 | 44 | Scope Clarification | 2025-04-27 | 2025-05-10 | 0 | Yes | 0
APT-0281 | Customer Onboarding Automation | Sprint 11 - 2025 | Zoya Fernandes | Medium | 5 | Done | 2025-06-02 | 2025-06-12 | 2025-06-17 | Engineering | High | 38 | 48 | Resource Constraint | 2025-05-25 | 2025-06-07 | 14 | Yes | 1
APT-0282 | Data Quality Remediation | Sprint 01 - 2025 | Vikram Singh | Low | 2 | In Progress | 2025-01-13 | 2025-01-19 |  | QA | Medium | 11 | 4 | Dependency Blocker | 2025-01-05 | 2025-01-18 | 0 | Yes | 0
APT-0283 | User Access Governance | Sprint 12 - 2025 | Vikram Singh | Medium | 3 | Testing | 2025-06-14 | 2025-06-25 |  | Engineering | Low | 14 | 13 | Requirement Change | 2025-06-08 | 2025-06-21 | 0 | Yes | 0
APT-0284 | Backlog Prioritization Framework | Sprint 02 - 2025 | Vikram Singh | Low | 3 | Done | 2025-01-26 | 2025-02-03 | 2025-02-03 | Product | Low | 12 | 11 | None | 2025-01-19 | 2025-02-01 | 7 | No | 1
APT-0285 | Operations SLA Dashboard | Sprint 05 - 2025 | Kabir Khan | High | 2 | Done | 2025-03-02 | 2025-03-05 | 2025-03-07 | Engineering | Low | 12 | 14 | Environment Issue | 2025-03-02 | 2025-03-15 | 4 | Yes | 1
APT-0286 | Sprint Reporting Hub | Sprint 04 - 2025 | Rohan Gupta | Medium | 3 | Done | 2025-02-18 | 2025-02-21 | 2025-02-21 | QA | Low | 13 | 16 | None | 2025-02-16 | 2025-03-01 | 2 | No | 1
APT-0287 | API Reliability Upgrade | Sprint 02 - 2025 | Kabir Khan | Medium | 8 | Done | 2025-01-19 | 2025-01-28 | 2025-01-27 | QA | Low | 29 | 36 | None | 2025-01-19 | 2025-02-01 | 7 | No | 1
APT-0288 | Data Quality Remediation | Sprint 10 - 2025 | Kabir Khan | Medium | 3 | Done | 2025-05-11 | 2025-05-17 | 2025-05-19 | QA | Low | 17 | 16 | Scope Clarification | 2025-05-11 | 2025-05-24 | 7 | Yes | 1
APT-0289 | Backlog Prioritization Framework | Sprint 07 - 2025 | Vikram Singh | Medium | 3 | Done | 2025-04-07 | 2025-04-14 | 2025-04-16 | Product | Medium | 11 | 10 | Resource Constraint | 2025-03-30 | 2025-04-12 | 8 | Yes | 1
APT-0290 | Backlog Prioritization Framework | Sprint 05 - 2025 | Kabir Khan | Low | 8 | Done | 2025-03-09 | 2025-03-12 | 2025-03-14 | Operations | High | 34 | 50 | Resource Constraint | 2025-03-02 | 2025-03-15 | 4 | Yes | 1
APT-0291 | Backlog Prioritization Framework | Sprint 02 - 2025 | Ananya Rao | Medium | 8 | Done | 2025-01-25 | 2025-02-03 | 2025-02-03 | Operations | Medium | 35 | 41 | None | 2025-01-19 | 2025-02-01 | 8 | No | 1
APT-0292 | Backlog Prioritization Framework | Sprint 11 - 2025 | Zoya Fernandes | Low | 13 | Done | 2025-05-25 | 2025-06-05 | 2025-06-06 | Operations | Low | 57 | 70 | UAT Feedback | 2025-05-25 | 2025-06-07 | 11 | Yes | 1
APT-0293 | API Reliability Upgrade | Sprint 11 - 2025 | Kabir Khan | Medium | 8 | Done | 2025-05-29 | 2025-06-01 | 2025-05-31 | Product | Medium | 41 | 37 | None | 2025-05-25 | 2025-06-07 | 1 | No | 1
APT-0294 | Mobile Experience Improvements | Sprint 05 - 2025 | Zoya Fernandes | Medium | 13 | Done | 2025-03-02 | 2025-03-06 | 2025-03-06 | Data Analytics | High | 56 | 64 | None | 2025-03-02 | 2025-03-15 | 3 | No | 1
APT-0295 | Operations SLA Dashboard | Sprint 09 - 2025 | Isha Sharma | Critical | 8 | Done | 2025-04-27 | 2025-05-06 | 2025-05-06 | QA | Low | 38 | 36 | None | 2025-04-27 | 2025-05-10 | 8 | No | 1
APT-0296 | Stakeholder Notification Service | Sprint 09 - 2025 | Arjun Menon | High | 5 | Done | 2025-04-28 | 2025-05-10 | 2025-05-13 | QA | High | 35 | 39 | UAT Feedback | 2025-04-27 | 2025-05-10 | 14 | Yes | 1
APT-0297 | Sprint Reporting Hub | Sprint 09 - 2025 | Vikram Singh | High | 2 | Done | 2025-05-01 | 2025-05-04 | 2025-05-06 | Operations | Low | 13 | 15 | Environment Issue | 2025-04-27 | 2025-05-10 | 4 | Yes | 1
APT-0298 | Operations SLA Dashboard | Sprint 01 - 2025 | Dev Patel | Medium | 8 | Done | 2025-01-11 | 2025-01-14 | 2025-01-13 | Engineering | Low | 28 | 28 | None | 2025-01-05 | 2025-01-18 | 1 | No | 1
APT-0299 | Customer Onboarding Automation | Sprint 02 - 2025 | Meera Nair | Low | 2 | Done | 2025-01-26 | 2025-02-05 | 2025-02-07 | Customer Success | Medium | 12 | 12 | Environment Issue | 2025-01-19 | 2025-02-01 | 11 | Yes | 1
APT-0300 | Billing Workflow Optimization | Sprint 06 - 2025 | Meera Nair | Medium | 3 | Done | 2025-03-16 | 2025-03-19 | 2025-03-17 | Customer Success | Low | 14 | 11 | None | 2025-03-16 | 2025-03-29 | 1 | No | 1
APT-0301 | Data Quality Remediation | Sprint 04 - 2025 | Sara Thomas | Medium | 1 | Done | 2025-02-23 | 2025-03-03 | 2025-03-01 | Data Analytics | High | 5 | 7 | None | 2025-02-16 | 2025-03-01 | 5 | No | 1
APT-0302 | Sprint Reporting Hub | Sprint 08 - 2025 | Meera Nair | Medium | 1 | Done | 2025-04-15 | 2025-04-24 | 2025-04-26 | Product | High | 6 | 8 | Dependency Blocker | 2025-04-13 | 2025-04-26 | 10 | Yes | 1
APT-0303 | Backlog Prioritization Framework | Sprint 11 - 2025 | Sara Thomas | Medium | 2 | Done | 2025-06-02 | 2025-06-09 | 2025-06-10 | Product | Low | 12 | 10 | Requirement Change | 2025-05-25 | 2025-06-07 | 7 | Yes | 1
APT-0304 | API Reliability Upgrade | Sprint 06 - 2025 | Zoya Fernandes | High | 3 | Done | 2025-03-23 | 2025-04-03 | 2025-04-03 | Product | Low | 18 | 16 | None | 2025-03-16 | 2025-03-29 | 10 | No | 1
APT-0305 | Stakeholder Notification Service | Sprint 08 - 2025 | Kabir Khan | High | 3 | In Progress | 2025-04-20 | 2025-04-23 |  | Engineering | High | 25 | 18 | UAT Feedback | 2025-04-13 | 2025-04-26 | 0 | Yes | 0
APT-0306 | User Access Governance | Sprint 05 - 2025 | Isha Sharma | High | 3 | Done | 2025-03-09 | 2025-03-12 | 2025-03-12 | Customer Success | Low | 15 | 16 | None | 2025-03-02 | 2025-03-15 | 2 | No | 1
APT-0307 | Customer Onboarding Automation | Sprint 05 - 2025 | Arjun Menon | Low | 3 | In Progress | 2025-03-03 | 2025-03-13 |  | Customer Success | Low | 9 | 6 | Scope Clarification | 2025-03-02 | 2025-03-15 | 0 | Yes | 0
APT-0308 | Customer Onboarding Automation | Sprint 12 - 2025 | Neha Verma | Medium | 2 | Testing | 2025-06-10 | 2025-06-22 |  | Engineering | Low | 11 | 10 | Resource Constraint | 2025-06-08 | 2025-06-21 | 0 | Yes | 0
APT-0309 | Customer Onboarding Automation | Sprint 05 - 2025 | Sara Thomas | Low | 3 | Done | 2025-03-09 | 2025-03-15 | 2025-03-16 | Product | Low | 13 | 13 | Scope Clarification | 2025-03-02 | 2025-03-15 | 6 | Yes | 1
APT-0310 | Operations SLA Dashboard | Sprint 10 - 2025 | Sara Thomas | High | 5 | Done | 2025-05-11 | 2025-05-20 | 2025-05-18 | Engineering | Low | 20 | 23 | None | 2025-05-11 | 2025-05-24 | 6 | No | 1
APT-0311 | Billing Workflow Optimization | Sprint 06 - 2025 | Kabir Khan | High | 2 | In Progress | 2025-03-23 | 2025-03-26 |  | Operations | Medium | 10 | 8 | Scope Clarification | 2025-03-16 | 2025-03-29 | 0 | Yes | 0
APT-0312 | Sprint Reporting Hub | Sprint 09 - 2025 | Vikram Singh | Medium | 3 | In Progress | 2025-04-28 | 2025-05-07 |  | Customer Success | Medium | 18 | 13 | UAT Feedback | 2025-04-27 | 2025-05-10 | 0 | Yes | 0
APT-0313 | Customer Onboarding Automation | Sprint 05 - 2025 | Meera Nair | Low | 3 | Done | 2025-03-03 | 2025-03-14 | 2025-03-16 | Data Analytics | Medium | 16 | 21 | Scope Clarification | 2025-03-02 | 2025-03-15 | 12 | Yes | 1
APT-0314 | User Access Governance | Sprint 09 - 2025 | Kabir Khan | Medium | 3 | Done | 2025-05-03 | 2025-05-06 | 2025-05-07 | Customer Success | Low | 14 | 17 | Scope Clarification | 2025-04-27 | 2025-05-10 | 3 | Yes | 1
APT-0315 | User Access Governance | Sprint 09 - 2025 | Isha Sharma | Medium | 5 | Done | 2025-04-28 | 2025-05-09 | 2025-05-09 | Customer Success | Low | 27 | 32 | None | 2025-04-27 | 2025-05-10 | 10 | No | 1
APT-0316 | Sprint Reporting Hub | Sprint 08 - 2025 | Arjun Menon | High | 2 | Done | 2025-04-19 | 2025-05-01 | 2025-05-02 | Product | Low | 10 | 11 | Environment Issue | 2025-04-13 | 2025-04-26 | 12 | Yes | 1
APT-0317 | API Reliability Upgrade | Sprint 05 - 2025 | Rohan Gupta | Medium | 3 | Done | 2025-03-09 | 2025-03-17 | 2025-03-16 | Operations | Low | 11 | 14 | None | 2025-03-02 | 2025-03-15 | 6 | No | 1
APT-0318 | Sprint Reporting Hub | Sprint 06 - 2025 | Isha Sharma | High | 5 | Testing | 2025-03-20 | 2025-03-30 |  | Customer Success | Medium | 22 | 21 | Requirement Change | 2025-03-16 | 2025-03-29 | 0 | Yes | 0
APT-0319 | Stakeholder Notification Service | Sprint 04 - 2025 | Rohan Gupta | High | 8 | Done | 2025-02-20 | 2025-02-25 | 2025-02-25 | QA | Low | 43 | 52 | None | 2025-02-16 | 2025-03-01 | 4 | No | 1
APT-0320 | Backlog Prioritization Framework | Sprint 01 - 2025 | Sara Thomas | Medium | 5 | Done | 2025-01-10 | 2025-01-16 | 2025-01-14 | Product | Low | 21 | 17 | None | 2025-01-05 | 2025-01-18 | 3 | No | 1
APT-0321 | User Access Governance | Sprint 03 - 2025 | Rohan Gupta | High | 2 | In Progress | 2025-02-03 | 2025-02-06 |  | Engineering | Medium | 11 | 8 | UAT Feedback | 2025-02-02 | 2025-02-15 | 0 | Yes | 0
APT-0322 | Data Quality Remediation | Sprint 06 - 2025 | Zoya Fernandes | Medium | 8 | Done | 2025-03-20 | 2025-03-26 | 2025-03-25 | Engineering | High | 57 | 63 | None | 2025-03-16 | 2025-03-29 | 4 | No | 1
APT-0323 | Stakeholder Notification Service | Sprint 09 - 2025 | Zoya Fernandes | High | 5 | Testing | 2025-05-02 | 2025-05-09 |  | Product | High | 34 | 39 | UAT Feedback | 2025-04-27 | 2025-05-10 | 0 | Yes | 0
APT-0324 | Billing Workflow Optimization | Sprint 12 - 2025 | Arjun Menon | High | 3 | To Do | 2025-06-16 | 2025-06-20 |  | Product | High | 19 | 0 | UAT Feedback | 2025-06-08 | 2025-06-21 | 0 | Yes | 0
APT-0325 | API Reliability Upgrade | Sprint 02 - 2025 | Neha Verma | High | 3 | Done | 2025-01-24 | 2025-02-01 | 2025-02-03 | Operations | Medium | 15 | 16 | Environment Issue | 2025-01-19 | 2025-02-01 | 9 | Yes | 1
APT-0326 | Customer Onboarding Automation | Sprint 05 - 2025 | Dev Patel | High | 2 | Done | 2025-03-05 | 2025-03-11 | 2025-03-12 | QA | Low | 11 | 10 | UAT Feedback | 2025-03-02 | 2025-03-15 | 6 | Yes | 1
APT-0327 | Data Quality Remediation | Sprint 05 - 2025 | Aarav Mehta | High | 3 | Done | 2025-03-03 | 2025-03-09 | 2025-03-08 | Customer Success | Medium | 15 | 20 | None | 2025-03-02 | 2025-03-15 | 4 | No | 1
APT-0328 | User Access Governance | Sprint 03 - 2025 | Isha Sharma | Medium | 13 | Done | 2025-02-02 | 2025-02-06 | 2025-02-06 | Operations | Medium | 81 | 111 | None | 2025-02-02 | 2025-02-15 | 3 | No | 1
APT-0329 | User Access Governance | Sprint 05 - 2025 | Aarav Mehta | Low | 5 | Done | 2025-03-09 | 2025-03-17 | 2025-03-18 | QA | Medium | 19 | 20 | Environment Issue | 2025-03-02 | 2025-03-15 | 8 | Yes | 1
APT-0330 | User Access Governance | Sprint 04 - 2025 | Isha Sharma | Low | 3 | Done | 2025-02-24 | 2025-03-06 | 2025-03-07 | Customer Success | Medium | 11 | 14 | Scope Clarification | 2025-02-16 | 2025-03-01 | 10 | Yes | 1
APT-0331 | API Reliability Upgrade | Sprint 01 - 2025 | Vikram Singh | Medium | 8 | Done | 2025-01-05 | 2025-01-17 | 2025-01-19 | Operations | Low | 45 | 38 | Dependency Blocker | 2025-01-05 | 2025-01-18 | 13 | Yes | 1
APT-0332 | Customer Onboarding Automation | Sprint 09 - 2025 | Zoya Fernandes | Medium | 2 | Done | 2025-05-02 | 2025-05-08 | 2025-05-10 | Product | High | 14 | 16 | Scope Clarification | 2025-04-27 | 2025-05-10 | 7 | Yes | 1
APT-0333 | Customer Onboarding Automation | Sprint 02 - 2025 | Zoya Fernandes | Low | 8 | Done | 2025-01-21 | 2025-01-26 | 2025-01-27 | Customer Success | Low | 35 | 34 | Resource Constraint | 2025-01-19 | 2025-02-01 | 5 | Yes | 1
APT-0334 | Customer Onboarding Automation | Sprint 08 - 2025 | Neha Verma | High | 3 | Done | 2025-04-20 | 2025-04-28 | 2025-04-29 | Data Analytics | Medium | 14 | 13 | Environment Issue | 2025-04-13 | 2025-04-26 | 8 | Yes | 1
APT-0335 | Sprint Reporting Hub | Sprint 02 - 2025 | Ananya Rao | Medium | 3 | Done | 2025-01-23 | 2025-01-26 | 2025-01-24 | Operations | High | 21 | 33 | None | 2025-01-19 | 2025-02-01 | 1 | No | 1
APT-0336 | Billing Workflow Optimization | Sprint 10 - 2025 | Aarav Mehta | High | 5 | Done | 2025-05-18 | 2025-05-29 | 2025-05-31 | QA | Low | 26 | 30 | Resource Constraint | 2025-05-11 | 2025-05-24 | 12 | Yes | 1
APT-0337 | Sprint Reporting Hub | Sprint 11 - 2025 | Arjun Menon | Low | 8 | Done | 2025-05-25 | 2025-06-01 | 2025-06-01 | Product | Low | 40 | 36 | None | 2025-05-25 | 2025-06-07 | 6 | No | 1
APT-0338 | Operations SLA Dashboard | Sprint 12 - 2025 | Dev Patel | Medium | 2 | Done | 2025-06-11 | 2025-06-18 | 2025-06-17 | Data Analytics | Low | 7 | 8 | None | 2025-06-08 | 2025-06-21 | 5 | No | 1
APT-0339 | Sprint Reporting Hub | Sprint 01 - 2025 | Aarav Mehta | Medium | 5 | Done | 2025-01-13 | 2025-01-23 | 2025-01-24 | Customer Success | High | 28 | 37 | Scope Clarification | 2025-01-05 | 2025-01-18 | 10 | Yes | 1
APT-0340 | User Access Governance | Sprint 11 - 2025 | Vikram Singh | Medium | 3 | Done | 2025-05-26 | 2025-05-29 | 2025-05-27 | Product | High | 20 | 20 | None | 2025-05-25 | 2025-06-07 | 1 | No | 1
APT-0341 | Stakeholder Notification Service | Sprint 05 - 2025 | Meera Nair | Medium | 13 | Done | 2025-03-06 | 2025-03-17 | 2025-03-19 | Engineering | Low | 74 | 74 | Resource Constraint | 2025-03-02 | 2025-03-15 | 12 | Yes | 1
APT-0342 | API Reliability Upgrade | Sprint 03 - 2025 | Vikram Singh | Medium | 5 | Done | 2025-02-08 | 2025-02-19 | 2025-02-18 | QA | Medium | 32 | 40 | None | 2025-02-02 | 2025-02-15 | 9 | No | 1
APT-0343 | API Reliability Upgrade | Sprint 08 - 2025 | Sara Thomas | High | 2 | Done | 2025-04-17 | 2025-04-24 | 2025-04-23 | Operations | Medium | 14 | 18 | None | 2025-04-13 | 2025-04-26 | 5 | No | 1
APT-0344 | Customer Onboarding Automation | Sprint 09 - 2025 | Aarav Mehta | Medium | 5 | Done | 2025-05-05 | 2025-05-15 | 2025-05-14 | QA | Low | 17 | 19 | None | 2025-04-27 | 2025-05-10 | 8 | No | 1
APT-0345 | Sprint Reporting Hub | Sprint 05 - 2025 | Meera Nair | Low | 8 | Done | 2025-03-10 | 2025-03-13 | 2025-03-12 | QA | Low | 40 | 37 | None | 2025-03-02 | 2025-03-15 | 1 | No | 1
APT-0346 | Billing Workflow Optimization | Sprint 01 - 2025 | Aarav Mehta | Medium | 2 | Done | 2025-01-08 | 2025-01-15 | 2025-01-15 | QA | Medium | 8 | 8 | None | 2025-01-05 | 2025-01-18 | 6 | No | 1
APT-0347 | Customer Onboarding Automation | Sprint 07 - 2025 | Isha Sharma | Critical | 3 | Done | 2025-04-04 | 2025-04-13 | 2025-04-15 | Operations | High | 21 | 29 | Resource Constraint | 2025-03-30 | 2025-04-12 | 10 | Yes | 1
APT-0348 | Billing Workflow Optimization | Sprint 09 - 2025 | Sara Thomas | High | 2 | Testing | 2025-05-01 | 2025-05-12 |  | QA | Medium | 14 | 14 | Environment Issue | 2025-04-27 | 2025-05-10 | 0 | Yes | 0
APT-0349 | Stakeholder Notification Service | Sprint 04 - 2025 | Aarav Mehta | Medium | 1 | Testing | 2025-02-20 | 2025-03-01 |  | Engineering | Medium | 5 | 5 | Scope Clarification | 2025-02-16 | 2025-03-01 | 0 | Yes | 0
APT-0350 | Backlog Prioritization Framework | Sprint 12 - 2025 | Sara Thomas | Critical | 3 | Done | 2025-06-08 | 2025-06-14 | 2025-06-13 | QA | Medium | 17 | 22 | None | 2025-06-08 | 2025-06-21 | 4 | No | 1
APT-0351 | API Reliability Upgrade | Sprint 03 - 2025 | Rohan Gupta | Medium | 3 | Testing | 2025-02-02 | 2025-02-08 |  | Product | Low | 11 | 9 | UAT Feedback | 2025-02-02 | 2025-02-15 | 0 | Yes | 0
APT-0352 | Sprint Reporting Hub | Sprint 09 - 2025 | Dev Patel | High | 8 | Done | 2025-04-30 | 2025-05-03 | 2025-05-04 | Product | Medium | 45 | 51 | Environment Issue | 2025-04-27 | 2025-05-10 | 3 | Yes | 1
APT-0353 | API Reliability Upgrade | Sprint 07 - 2025 | Dev Patel | Low | 3 | Done | 2025-03-31 | 2025-04-06 | 2025-04-06 | Product | Low | 16 | 15 | None | 2025-03-30 | 2025-04-12 | 5 | No | 1
APT-0354 | Stakeholder Notification Service | Sprint 03 - 2025 | Ananya Rao | Medium | 2 | To Do | 2025-02-07 | 2025-02-14 |  | Engineering | Low | 11 | 0 | Scope Clarification | 2025-02-02 | 2025-02-15 | 0 | Yes | 0
APT-0355 | Mobile Experience Improvements | Sprint 03 - 2025 | Vikram Singh | Medium | 8 | Done | 2025-02-08 | 2025-02-11 | 2025-02-11 | Product | Low | 45 | 47 | None | 2025-02-02 | 2025-02-15 | 2 | No | 1
APT-0356 | Mobile Experience Improvements | Sprint 12 - 2025 | Arjun Menon | Medium | 8 | Done | 2025-06-14 | 2025-06-26 | 2025-06-26 | Engineering | Low | 34 | 42 | None | 2025-06-08 | 2025-06-21 | 11 | No | 1
APT-0357 | Mobile Experience Improvements | Sprint 08 - 2025 | Isha Sharma | High | 3 | Done | 2025-04-16 | 2025-04-19 | 2025-04-19 | Customer Success | Medium | 20 | 26 | None | 2025-04-13 | 2025-04-26 | 2 | No | 1
APT-0358 | User Access Governance | Sprint 08 - 2025 | Sara Thomas | Medium | 13 | Done | 2025-04-16 | 2025-04-24 | 2025-04-24 | QA | Low | 64 | 54 | None | 2025-04-13 | 2025-04-26 | 7 | No | 1
APT-0359 | Billing Workflow Optimization | Sprint 08 - 2025 | Zoya Fernandes | Medium | 5 | Done | 2025-04-20 | 2025-04-29 | 2025-04-29 | QA | Low | 22 | 25 | None | 2025-04-13 | 2025-04-26 | 8 | No | 1
APT-0360 | Backlog Prioritization Framework | Sprint 01 - 2025 | Vikram Singh | Critical | 3 | Done | 2025-01-11 | 2025-01-14 | 2025-01-15 | Operations | Medium | 16 | 21 | Environment Issue | 2025-01-05 | 2025-01-18 | 3 | Yes | 1
APT-0361 | User Access Governance | Sprint 10 - 2025 | Arjun Menon | Critical | 13 | Done | 2025-05-17 | 2025-05-29 | 2025-05-31 | Data Analytics | High | 109 | 143 | UAT Feedback | 2025-05-11 | 2025-05-24 | 13 | Yes | 1
APT-0362 | Data Quality Remediation | Sprint 07 - 2025 | Ananya Rao | High | 8 | In Progress | 2025-04-02 | 2025-04-12 |  | Customer Success | Medium | 50 | 24 | Environment Issue | 2025-03-30 | 2025-04-12 | 0 | Yes | 0
APT-0363 | Backlog Prioritization Framework | Sprint 09 - 2025 | Meera Nair | High | 3 | Done | 2025-04-27 | 2025-05-04 | 2025-05-04 | Engineering | Medium | 21 | 24 | None | 2025-04-27 | 2025-05-10 | 6 | No | 1
APT-0364 | Billing Workflow Optimization | Sprint 02 - 2025 | Aarav Mehta | Critical | 1 | In Progress | 2025-01-19 | 2025-01-24 |  | Customer Success | Medium | 6 | 4 | UAT Feedback | 2025-01-19 | 2025-02-01 | 0 | Yes | 0
APT-0365 | Stakeholder Notification Service | Sprint 09 - 2025 | Neha Verma | Low | 3 | In Progress | 2025-05-02 | 2025-05-09 |  | Operations | Medium | 19 | 14 | Environment Issue | 2025-04-27 | 2025-05-10 | 0 | Yes | 0
APT-0366 | Stakeholder Notification Service | Sprint 07 - 2025 | Arjun Menon | Medium | 5 | Done | 2025-04-07 | 2025-04-17 | 2025-04-18 | Customer Success | Low | 21 | 24 | UAT Feedback | 2025-03-30 | 2025-04-12 | 10 | Yes | 1
APT-0367 | Billing Workflow Optimization | Sprint 07 - 2025 | Rohan Gupta | Medium | 8 | Testing | 2025-04-06 | 2025-04-16 |  | Engineering | Low | 35 | 26 | Environment Issue | 2025-03-30 | 2025-04-12 | 0 | Yes | 0
APT-0368 | Mobile Experience Improvements | Sprint 12 - 2025 | Kabir Khan | Medium | 2 | In Progress | 2025-06-11 | 2025-06-14 |  | Engineering | Low | 11 | 4 | Requirement Change | 2025-06-08 | 2025-06-21 | 0 | Yes | 0
APT-0369 | Data Quality Remediation | Sprint 08 - 2025 | Vikram Singh | Medium | 5 | Done | 2025-04-16 | 2025-04-20 | 2025-04-18 | Product | Low | 20 | 17 | None | 2025-04-13 | 2025-04-26 | 1 | No | 1
APT-0370 | Sprint Reporting Hub | Sprint 11 - 2025 | Sara Thomas | Medium | 8 | Done | 2025-06-01 | 2025-06-04 | 2025-06-06 | QA | Medium | 35 | 32 | Resource Constraint | 2025-05-25 | 2025-06-07 | 4 | Yes | 1
APT-0371 | Billing Workflow Optimization | Sprint 08 - 2025 | Vikram Singh | High | 2 | Testing | 2025-04-20 | 2025-04-26 |  | QA | Medium | 10 | 9 | Scope Clarification | 2025-04-13 | 2025-04-26 | 0 | Yes | 0
APT-0372 | Billing Workflow Optimization | Sprint 12 - 2025 | Sara Thomas | Medium | 3 | Done | 2025-06-15 | 2025-06-26 | 2025-06-25 | Engineering | Low | 15 | 19 | None | 2025-06-08 | 2025-06-21 | 9 | No | 1
APT-0373 | Backlog Prioritization Framework | Sprint 02 - 2025 | Ananya Rao | Medium | 5 | In Progress | 2025-01-21 | 2025-01-24 |  | Data Analytics | Low | 21 | 9 | Requirement Change | 2025-01-19 | 2025-02-01 | 0 | Yes | 0
APT-0374 | Customer Onboarding Automation | Sprint 02 - 2025 | Zoya Fernandes | Medium | 5 | Done | 2025-01-26 | 2025-02-06 | 2025-02-09 | Data Analytics | Medium | 31 | 34 | Environment Issue | 2025-01-19 | 2025-02-01 | 13 | Yes | 1
APT-0375 | Operations SLA Dashboard | Sprint 06 - 2025 | Aarav Mehta | Medium | 13 | Done | 2025-03-17 | 2025-03-24 | 2025-03-25 | Product | Medium | 71 | 71 | UAT Feedback | 2025-03-16 | 2025-03-29 | 7 | Yes | 1
APT-0376 | API Reliability Upgrade | Sprint 05 - 2025 | Dev Patel | High | 3 | Testing | 2025-03-06 | 2025-03-15 |  | Data Analytics | Low | 12 | 12 | Resource Constraint | 2025-03-02 | 2025-03-15 | 0 | Yes | 0
APT-0377 | Operations SLA Dashboard | Sprint 05 - 2025 | Zoya Fernandes | Medium | 2 | Done | 2025-03-05 | 2025-03-14 | 2025-03-14 | Engineering | Medium | 13 | 17 | None | 2025-03-02 | 2025-03-15 | 8 | No | 1
APT-0378 | Mobile Experience Improvements | Sprint 03 - 2025 | Kabir Khan | Medium | 3 | Done | 2025-02-04 | 2025-02-08 | 2025-02-08 | Data Analytics | Low | 14 | 14 | None | 2025-02-02 | 2025-02-15 | 3 | No | 1
APT-0379 | Sprint Reporting Hub | Sprint 12 - 2025 | Dev Patel | Medium | 3 | In Progress | 2025-06-14 | 2025-06-22 |  | Product | Low | 14 | 5 | Resource Constraint | 2025-06-08 | 2025-06-21 | 0 | Yes | 0
APT-0380 | API Reliability Upgrade | Sprint 11 - 2025 | Dev Patel | Medium | 13 | Testing | 2025-06-01 | 2025-06-10 |  | Engineering | Low | 54 | 54 | Resource Constraint | 2025-05-25 | 2025-06-07 | 0 | Yes | 0
APT-0381 | Customer Onboarding Automation | Sprint 06 - 2025 | Meera Nair | High | 2 | Done | 2025-03-24 | 2025-04-02 | 2025-04-03 | QA | Medium | 13 | 18 | UAT Feedback | 2025-03-16 | 2025-03-29 | 9 | Yes | 1
APT-0382 | User Access Governance | Sprint 10 - 2025 | Meera Nair | High | 2 | Done | 2025-05-17 | 2025-05-25 | 2025-05-25 | Product | Medium | 11 | 13 | None | 2025-05-11 | 2025-05-24 | 7 | No | 1
APT-0383 | Billing Workflow Optimization | Sprint 08 - 2025 | Sara Thomas | High | 3 | In Progress | 2025-04-20 | 2025-05-01 |  | Data Analytics | Low | 17 | 7 | Environment Issue | 2025-04-13 | 2025-04-26 | 0 | Yes | 0
APT-0384 | Sprint Reporting Hub | Sprint 06 - 2025 | Dev Patel | Low | 5 | Done | 2025-03-17 | 2025-03-26 | 2025-03-25 | Product | Low | 26 | 22 | None | 2025-03-16 | 2025-03-29 | 7 | No | 1
APT-0385 | Billing Workflow Optimization | Sprint 09 - 2025 | Meera Nair | Medium | 5 | Done | 2025-04-30 | 2025-05-06 | 2025-05-06 | Engineering | High | 28 | 28 | None | 2025-04-27 | 2025-05-10 | 5 | No | 1
APT-0386 | Data Quality Remediation | Sprint 08 - 2025 | Dev Patel | Medium | 3 | Done | 2025-04-17 | 2025-04-23 | 2025-04-22 | Customer Success | Medium | 17 | 23 | None | 2025-04-13 | 2025-04-26 | 4 | No | 1
APT-0387 | Sprint Reporting Hub | Sprint 02 - 2025 | Ananya Rao | Critical | 3 | Done | 2025-01-22 | 2025-01-30 | 2025-01-30 | Customer Success | Medium | 24 | 32 | None | 2025-01-19 | 2025-02-01 | 7 | No | 1
APT-0388 | API Reliability Upgrade | Sprint 08 - 2025 | Dev Patel | Medium | 5 | Testing | 2025-04-16 | 2025-04-21 |  | Engineering | Low | 25 | 19 | UAT Feedback | 2025-04-13 | 2025-04-26 | 0 | Yes | 0
APT-0389 | Backlog Prioritization Framework | Sprint 05 - 2025 | Sara Thomas | High | 3 | Done | 2025-03-07 | 2025-03-18 | 2025-03-18 | QA | Low | 11 | 9 | None | 2025-03-02 | 2025-03-15 | 10 | No | 1
APT-0390 | Backlog Prioritization Framework | Sprint 06 - 2025 | Rohan Gupta | Critical | 3 | Done | 2025-03-21 | 2025-03-27 | 2025-03-26 | Customer Success | High | 17 | 19 | None | 2025-03-16 | 2025-03-29 | 4 | No | 1
APT-0391 | Mobile Experience Improvements | Sprint 06 - 2025 | Vikram Singh | Low | 3 | Done | 2025-03-18 | 2025-03-22 | 2025-03-21 | Product | High | 19 | 23 | None | 2025-03-16 | 2025-03-29 | 2 | No | 1
APT-0392 | Billing Workflow Optimization | Sprint 01 - 2025 | Zoya Fernandes | High | 5 | Done | 2025-01-05 | 2025-01-08 | 2025-01-09 | Customer Success | Low | 26 | 30 | Requirement Change | 2025-01-05 | 2025-01-18 | 3 | Yes | 1
APT-0393 | Stakeholder Notification Service | Sprint 10 - 2025 | Dev Patel | Low | 2 | Done | 2025-05-13 | 2025-05-20 | 2025-05-19 | Product | Low | 7 | 9 | None | 2025-05-11 | 2025-05-24 | 5 | No | 1
APT-0394 | Backlog Prioritization Framework | Sprint 01 - 2025 | Sara Thomas | Medium | 3 | Done | 2025-01-09 | 2025-01-12 | 2025-01-12 | Engineering | Low | 11 | 12 | None | 2025-01-05 | 2025-01-18 | 2 | No | 1
APT-0395 | User Access Governance | Sprint 09 - 2025 | Meera Nair | Medium | 3 | Testing | 2025-05-03 | 2025-05-12 |  | Product | Low | 11 | 8 | Environment Issue | 2025-04-27 | 2025-05-10 | 0 | Yes | 0
APT-0396 | Sprint Reporting Hub | Sprint 05 - 2025 | Meera Nair | High | 5 | Done | 2025-03-09 | 2025-03-20 | 2025-03-20 | Product | Low | 28 | 29 | None | 2025-03-02 | 2025-03-15 | 10 | No | 1
APT-0397 | Customer Onboarding Automation | Sprint 08 - 2025 | Rohan Gupta | Critical | 13 | Done | 2025-04-14 | 2025-04-26 | 2025-04-28 | Operations | High | 82 | 88 | Requirement Change | 2025-04-13 | 2025-04-26 | 13 | Yes | 1
APT-0398 | Mobile Experience Improvements | Sprint 05 - 2025 | Isha Sharma | Medium | 3 | In Progress | 2025-03-06 | 2025-03-17 |  | QA | Low | 12 | 9 | Requirement Change | 2025-03-02 | 2025-03-15 | 0 | Yes | 0
APT-0399 | User Access Governance | Sprint 07 - 2025 | Ananya Rao | Low | 5 | Done | 2025-03-30 | 2025-04-02 | 2025-04-03 | Operations | Low | 22 | 19 | Environment Issue | 2025-03-30 | 2025-04-12 | 3 | Yes | 1
APT-0400 | Backlog Prioritization Framework | Sprint 06 - 2025 | Vikram Singh | Medium | 3 | Done | 2025-03-22 | 2025-03-25 | 2025-03-26 | Engineering | Medium | 19 | 17 | UAT Feedback | 2025-03-16 | 2025-03-29 | 3 | Yes | 1
APT-0401 | Data Quality Remediation | Sprint 04 - 2025 | Kabir Khan | High | 8 | Testing | 2025-02-20 | 2025-02-26 |  | QA | High | 50 | 48 | Resource Constraint | 2025-02-16 | 2025-03-01 | 0 | Yes | 0
APT-0402 | Data Quality Remediation | Sprint 03 - 2025 | Neha Verma | Medium | 1 | To Do | 2025-02-02 | 2025-02-14 |  | Data Analytics | Low | 4 | 0 | Dependency Blocker | 2025-02-02 | 2025-02-15 | 0 | Yes | 0
APT-0403 | Operations SLA Dashboard | Sprint 04 - 2025 | Rohan Gupta | Low | 8 | Done | 2025-02-21 | 2025-03-01 | 2025-03-02 | Operations | Low | 34 | 28 | Requirement Change | 2025-02-16 | 2025-03-01 | 8 | Yes | 1
APT-0404 | Stakeholder Notification Service | Sprint 07 - 2025 | Meera Nair | Critical | 5 | Done | 2025-04-06 | 2025-04-17 | 2025-04-19 | Engineering | Low | 27 | 31 | Environment Issue | 2025-03-30 | 2025-04-12 | 12 | Yes | 1
APT-0405 | Billing Workflow Optimization | Sprint 11 - 2025 | Sara Thomas | Medium | 3 | Done | 2025-05-27 | 2025-06-04 | 2025-06-04 | Customer Success | Medium | 11 | 10 | None | 2025-05-25 | 2025-06-07 | 7 | No | 1
APT-0406 | Operations SLA Dashboard | Sprint 05 - 2025 | Arjun Menon | High | 8 | Done | 2025-03-02 | 2025-03-08 | 2025-03-07 | Data Analytics | Low | 44 | 48 | None | 2025-03-02 | 2025-03-15 | 4 | No | 1
APT-0407 | Customer Onboarding Automation | Sprint 05 - 2025 | Sara Thomas | Low | 8 | Done | 2025-03-09 | 2025-03-12 | 2025-03-14 | Operations | Medium | 32 | 33 | UAT Feedback | 2025-03-02 | 2025-03-15 | 4 | Yes | 1
APT-0408 | Operations SLA Dashboard | Sprint 07 - 2025 | Rohan Gupta | High | 2 | To Do | 2025-04-02 | 2025-04-12 |  | Operations | High | 12 | 0 | Dependency Blocker | 2025-03-30 | 2025-04-12 | 0 | Yes | 0
APT-0409 | API Reliability Upgrade | Sprint 07 - 2025 | Sara Thomas | High | 2 | Done | 2025-03-30 | 2025-04-03 | 2025-04-03 | Customer Success | Low | 13 | 14 | None | 2025-03-30 | 2025-04-12 | 3 | No | 1
APT-0410 | Sprint Reporting Hub | Sprint 04 - 2025 | Aarav Mehta | High | 13 | Done | 2025-02-16 | 2025-02-20 | 2025-02-20 | Data Analytics | Low | 78 | 66 | None | 2025-02-16 | 2025-03-01 | 3 | No | 1
APT-0411 | Billing Workflow Optimization | Sprint 12 - 2025 | Aarav Mehta | High | 2 | Done | 2025-06-09 | 2025-06-17 | 2025-06-17 | Operations | Low | 10 | 8 | None | 2025-06-08 | 2025-06-21 | 7 | No | 1
APT-0412 | Backlog Prioritization Framework | Sprint 11 - 2025 | Zoya Fernandes | Medium | 1 | In Progress | 2025-05-28 | 2025-06-06 |  | Customer Success | High | 5 | 4 | Dependency Blocker | 2025-05-25 | 2025-06-07 | 0 | Yes | 0
APT-0413 | Sprint Reporting Hub | Sprint 12 - 2025 | Aarav Mehta | Medium | 2 | Testing | 2025-06-13 | 2025-06-23 |  | Data Analytics | Medium | 10 | 11 | UAT Feedback | 2025-06-08 | 2025-06-21 | 0 | Yes | 0
APT-0414 | API Reliability Upgrade | Sprint 04 - 2025 | Sara Thomas | Medium | 2 | In Progress | 2025-02-17 | 2025-02-25 |  | Data Analytics | Medium | 12 | 5 | Scope Clarification | 2025-02-16 | 2025-03-01 | 0 | Yes | 0
APT-0415 | Billing Workflow Optimization | Sprint 09 - 2025 | Zoya Fernandes | High | 3 | Done | 2025-04-29 | 2025-05-07 | 2025-05-08 | Data Analytics | Low | 11 | 13 | Requirement Change | 2025-04-27 | 2025-05-10 | 8 | Yes | 1
APT-0416 | Data Quality Remediation | Sprint 08 - 2025 | Ananya Rao | Medium | 8 | Done | 2025-04-17 | 2025-04-29 | 2025-04-30 | Product | Low | 27 | 32 | Dependency Blocker | 2025-04-13 | 2025-04-26 | 12 | Yes | 1
APT-0417 | API Reliability Upgrade | Sprint 12 - 2025 | Isha Sharma | Medium | 5 | Done | 2025-06-09 | 2025-06-20 | 2025-06-22 | Engineering | Medium | 19 | 25 | Environment Issue | 2025-06-08 | 2025-06-21 | 12 | Yes | 1
APT-0418 | Sprint Reporting Hub | Sprint 11 - 2025 | Zoya Fernandes | Medium | 5 | Done | 2025-05-28 | 2025-06-06 | 2025-06-06 | Data Analytics | Low | 29 | 30 | None | 2025-05-25 | 2025-06-07 | 8 | No | 1
APT-0419 | Stakeholder Notification Service | Sprint 03 - 2025 | Kabir Khan | Low | 1 | Done | 2025-02-07 | 2025-02-16 | 2025-02-16 | QA | Low | 5 | 6 | None | 2025-02-02 | 2025-02-15 | 8 | No | 1
APT-0420 | Backlog Prioritization Framework | Sprint 01 - 2025 | Arjun Menon | High | 3 | Done | 2025-01-08 | 2025-01-17 | 2025-01-17 | QA | Medium | 16 | 17 | None | 2025-01-05 | 2025-01-18 | 8 | No | 1
APT-0421 | Backlog Prioritization Framework | Sprint 03 - 2025 | Isha Sharma | Medium | 2 | Done | 2025-02-06 | 2025-02-13 | 2025-02-13 | Customer Success | High | 14 | 20 | None | 2025-02-02 | 2025-02-15 | 6 | No | 1
APT-0422 | Sprint Reporting Hub | Sprint 08 - 2025 | Neha Verma | Medium | 5 | Done | 2025-04-17 | 2025-04-28 | 2025-04-28 | Customer Success | Low | 28 | 23 | None | 2025-04-13 | 2025-04-26 | 10 | No | 1
APT-0423 | Mobile Experience Improvements | Sprint 01 - 2025 | Dev Patel | Medium | 5 | Done | 2025-01-10 | 2025-01-22 | 2025-01-22 | QA | Low | 23 | 28 | None | 2025-01-05 | 2025-01-18 | 11 | No | 1
APT-0424 | Billing Workflow Optimization | Sprint 05 - 2025 | Neha Verma | Medium | 3 | Done | 2025-03-02 | 2025-03-11 | 2025-03-13 | Product | Low | 11 | 10 | Environment Issue | 2025-03-02 | 2025-03-15 | 10 | Yes | 1
APT-0425 | Stakeholder Notification Service | Sprint 02 - 2025 | Kabir Khan | Low | 13 | Done | 2025-01-24 | 2025-02-02 | 2025-02-04 | Engineering | Medium | 59 | 71 | Dependency Blocker | 2025-01-19 | 2025-02-01 | 10 | Yes | 1
APT-0426 | Stakeholder Notification Service | Sprint 11 - 2025 | Kabir Khan | Medium | 5 | Done | 2025-05-28 | 2025-06-08 | 2025-06-09 | Data Analytics | High | 29 | 32 | Dependency Blocker | 2025-05-25 | 2025-06-07 | 11 | Yes | 1
APT-0427 | Mobile Experience Improvements | Sprint 01 - 2025 | Vikram Singh | High | 8 | Done | 2025-01-10 | 2025-01-15 | 2025-01-17 | Product | Medium | 33 | 42 | Requirement Change | 2025-01-05 | 2025-01-18 | 6 | Yes | 1
APT-0428 | Mobile Experience Improvements | Sprint 03 - 2025 | Sara Thomas | Critical | 5 | To Do | 2025-02-05 | 2025-02-10 |  | Data Analytics | Low | 32 | 0 | UAT Feedback | 2025-02-02 | 2025-02-15 | 0 | Yes | 0
APT-0429 | API Reliability Upgrade | Sprint 03 - 2025 | Arjun Menon | High | 3 | Testing | 2025-02-07 | 2025-02-10 |  | Customer Success | Low | 13 | 10 | Dependency Blocker | 2025-02-02 | 2025-02-15 | 0 | Yes | 0
APT-0430 | Mobile Experience Improvements | Sprint 06 - 2025 | Isha Sharma | Medium | 8 | Testing | 2025-03-23 | 2025-04-02 |  | Engineering | Low | 46 | 42 | Environment Issue | 2025-03-16 | 2025-03-29 | 0 | Yes | 0
APT-0431 | Sprint Reporting Hub | Sprint 10 - 2025 | Rohan Gupta | Medium | 5 | Done | 2025-05-17 | 2025-05-26 | 2025-05-24 | Engineering | Medium | 32 | 40 | None | 2025-05-11 | 2025-05-24 | 6 | No | 1
APT-0432 | Sprint Reporting Hub | Sprint 10 - 2025 | Kabir Khan | Medium | 3 | To Do | 2025-05-18 | 2025-05-22 |  | Operations | Medium | 13 | 0 | Environment Issue | 2025-05-11 | 2025-05-24 | 0 | Yes | 0
APT-0433 | Customer Onboarding Automation | Sprint 09 - 2025 | Arjun Menon | Low | 13 | To Do | 2025-05-01 | 2025-05-07 |  | Operations | Low | 64 | 0 | Dependency Blocker | 2025-04-27 | 2025-05-10 | 0 | Yes | 0
APT-0434 | API Reliability Upgrade | Sprint 03 - 2025 | Meera Nair | Medium | 3 | Done | 2025-02-02 | 2025-02-12 | 2025-02-14 | Operations | Medium | 19 | 23 | Scope Clarification | 2025-02-02 | 2025-02-15 | 11 | Yes | 1
APT-0435 | Billing Workflow Optimization | Sprint 04 - 2025 | Aarav Mehta | High | 3 | Done | 2025-02-16 | 2025-02-25 | 2025-02-26 | Engineering | High | 22 | 34 | Dependency Blocker | 2025-02-16 | 2025-03-01 | 9 | Yes | 1
APT-0436 | Mobile Experience Improvements | Sprint 09 - 2025 | Kabir Khan | Critical | 3 | Done | 2025-04-29 | 2025-05-07 | 2025-05-05 | Customer Success | Low | 14 | 17 | None | 2025-04-27 | 2025-05-10 | 5 | No | 1
APT-0437 | Data Quality Remediation | Sprint 09 - 2025 | Rohan Gupta | Medium | 2 | Testing | 2025-05-03 | 2025-05-12 |  | Operations | Low | 8 | 7 | Resource Constraint | 2025-04-27 | 2025-05-10 | 0 | Yes | 0
APT-0438 | User Access Governance | Sprint 10 - 2025 | Arjun Menon | High | 2 | To Do | 2025-05-17 | 2025-05-29 |  | QA | Low | 11 | 0 | Scope Clarification | 2025-05-11 | 2025-05-24 | 0 | Yes | 0
APT-0439 | User Access Governance | Sprint 10 - 2025 | Kabir Khan | Low | 3 | Done | 2025-05-17 | 2025-05-24 | 2025-05-26 | Operations | High | 21 | 29 | Requirement Change | 2025-05-11 | 2025-05-24 | 8 | Yes | 1
APT-0440 | Billing Workflow Optimization | Sprint 03 - 2025 | Kabir Khan | Medium | 5 | Done | 2025-02-06 | 2025-02-10 | 2025-02-10 | QA | Low | 29 | 25 | None | 2025-02-02 | 2025-02-15 | 3 | No | 1
APT-0441 | Stakeholder Notification Service | Sprint 08 - 2025 | Neha Verma | High | 8 | Done | 2025-04-17 | 2025-04-25 | 2025-04-24 | Engineering | Low | 35 | 35 | None | 2025-04-13 | 2025-04-26 | 6 | No | 1
APT-0442 | Sprint Reporting Hub | Sprint 09 - 2025 | Rohan Gupta | Critical | 13 | To Do | 2025-05-04 | 2025-05-08 |  | Customer Success | Low | 74 | 0 | UAT Feedback | 2025-04-27 | 2025-05-10 | 0 | Yes | 0
APT-0443 | Data Quality Remediation | Sprint 06 - 2025 | Zoya Fernandes | Medium | 5 | Done | 2025-03-18 | 2025-03-30 | 2025-03-30 | QA | High | 30 | 46 | None | 2025-03-16 | 2025-03-29 | 11 | No | 1
APT-0444 | Billing Workflow Optimization | Sprint 01 - 2025 | Kabir Khan | Low | 5 | Done | 2025-01-11 | 2025-01-19 | 2025-01-19 | Engineering | Medium | 28 | 39 | None | 2025-01-05 | 2025-01-18 | 7 | No | 1
APT-0445 | Backlog Prioritization Framework | Sprint 08 - 2025 | Isha Sharma | Low | 2 | Done | 2025-04-15 | 2025-04-22 | 2025-04-22 | Data Analytics | Low | 11 | 13 | None | 2025-04-13 | 2025-04-26 | 6 | No | 1
APT-0446 | Operations SLA Dashboard | Sprint 08 - 2025 | Aarav Mehta | Low | 8 | Testing | 2025-04-18 | 2025-04-27 |  | Engineering | High | 42 | 53 | Requirement Change | 2025-04-13 | 2025-04-26 | 0 | Yes | 0
APT-0447 | Data Quality Remediation | Sprint 06 - 2025 | Meera Nair | Low | 8 | Done | 2025-03-18 | 2025-03-21 | 2025-03-21 | QA | Medium | 42 | 45 | None | 2025-03-16 | 2025-03-29 | 2 | No | 1
APT-0448 | Sprint Reporting Hub | Sprint 04 - 2025 | Isha Sharma | Medium | 5 | Done | 2025-02-18 | 2025-02-23 | 2025-02-23 | Engineering | Low | 24 | 29 | None | 2025-02-16 | 2025-03-01 | 4 | No | 1
APT-0449 | Stakeholder Notification Service | Sprint 12 - 2025 | Arjun Menon | Medium | 1 | Done | 2025-06-11 | 2025-06-14 | 2025-06-12 | Engineering | Medium | 4 | 4 | None | 2025-06-08 | 2025-06-21 | 1 | No | 1
APT-0450 | Sprint Reporting Hub | Sprint 05 - 2025 | Arjun Menon | Medium | 1 | Done | 2025-03-07 | 2025-03-17 | 2025-03-17 | Operations | Low | 4 | 5 | None | 2025-03-02 | 2025-03-15 | 9 | No | 1
APT-0451 | Mobile Experience Improvements | Sprint 07 - 2025 | Isha Sharma | Medium | 3 | Testing | 2025-03-30 | 2025-04-04 |  | Operations | Medium | 11 | 12 | Requirement Change | 2025-03-30 | 2025-04-12 | 0 | Yes | 0
APT-0452 | User Access Governance | Sprint 07 - 2025 | Arjun Menon | High | 3 | Done | 2025-04-02 | 2025-04-05 | 2025-04-05 | Product | Low | 18 | 22 | None | 2025-03-30 | 2025-04-12 | 2 | No | 1
APT-0453 | Backlog Prioritization Framework | Sprint 06 - 2025 | Ananya Rao | Medium | 5 | Done | 2025-03-22 | 2025-03-31 | 2025-03-31 | Engineering | Low | 27 | 31 | None | 2025-03-16 | 2025-03-29 | 8 | No | 1
APT-0454 | Customer Onboarding Automation | Sprint 04 - 2025 | Ananya Rao | High | 3 | To Do | 2025-02-22 | 2025-03-02 |  | Operations | Low | 11 | 0 | Environment Issue | 2025-02-16 | 2025-03-01 | 0 | Yes | 0
APT-0455 | Backlog Prioritization Framework | Sprint 02 - 2025 | Rohan Gupta | High | 3 | Done | 2025-01-19 | 2025-01-25 | 2025-01-26 | Operations | Low | 16 | 14 | Scope Clarification | 2025-01-19 | 2025-02-01 | 6 | Yes | 1
APT-0456 | User Access Governance | Sprint 04 - 2025 | Zoya Fernandes | Medium | 3 | Done | 2025-02-20 | 2025-02-27 | 2025-03-01 | Product | Medium | 12 | 11 | Scope Clarification | 2025-02-16 | 2025-03-01 | 8 | Yes | 1
APT-0457 | Backlog Prioritization Framework | Sprint 04 - 2025 | Arjun Menon | Low | 1 | Testing | 2025-02-22 | 2025-02-27 |  | Product | Medium | 4 | 3 | Dependency Blocker | 2025-02-16 | 2025-03-01 | 0 | Yes | 0
APT-0458 | Customer Onboarding Automation | Sprint 05 - 2025 | Zoya Fernandes | High | 3 | Done | 2025-03-05 | 2025-03-10 | 2025-03-11 | Data Analytics | High | 23 | 25 | Scope Clarification | 2025-03-02 | 2025-03-15 | 5 | Yes | 1
APT-0459 | Customer Onboarding Automation | Sprint 07 - 2025 | Arjun Menon | Low | 13 | In Progress | 2025-04-02 | 2025-04-14 |  | Product | High | 65 | 48 | Resource Constraint | 2025-03-30 | 2025-04-12 | 0 | Yes | 0
APT-0460 | Operations SLA Dashboard | Sprint 03 - 2025 | Ananya Rao | Low | 2 | In Progress | 2025-02-04 | 2025-02-12 |  | Customer Success | Low | 7 | 4 | Dependency Blocker | 2025-02-02 | 2025-02-15 | 0 | Yes | 0
APT-0461 | Billing Workflow Optimization | Sprint 02 - 2025 | Rohan Gupta | Medium | 1 | Done | 2025-01-25 | 2025-01-29 | 2025-01-31 | Operations | Medium | 6 | 7 | Environment Issue | 2025-01-19 | 2025-02-01 | 5 | Yes | 1
APT-0462 | Stakeholder Notification Service | Sprint 11 - 2025 | Aarav Mehta | High | 5 | Done | 2025-05-29 | 2025-06-08 | 2025-06-08 | Data Analytics | Low | 24 | 23 | None | 2025-05-25 | 2025-06-07 | 9 | No | 1
APT-0463 | Billing Workflow Optimization | Sprint 12 - 2025 | Zoya Fernandes | High | 2 | To Do | 2025-06-13 | 2025-06-21 |  | QA | Low | 11 | 0 | Scope Clarification | 2025-06-08 | 2025-06-21 | 0 | Yes | 0
APT-0464 | Billing Workflow Optimization | Sprint 10 - 2025 | Vikram Singh | Low | 8 | Done | 2025-05-11 | 2025-05-19 | 2025-05-19 | Operations | Low | 41 | 35 | None | 2025-05-11 | 2025-05-24 | 7 | No | 1
APT-0465 | Customer Onboarding Automation | Sprint 02 - 2025 | Arjun Menon | Low | 8 | Testing | 2025-01-22 | 2025-01-30 |  | Engineering | Low | 31 | 22 | Requirement Change | 2025-01-19 | 2025-02-01 | 0 | Yes | 0
APT-0466 | Billing Workflow Optimization | Sprint 05 - 2025 | Meera Nair | High | 5 | Done | 2025-03-08 | 2025-03-17 | 2025-03-18 | Engineering | Low | 25 | 27 | Environment Issue | 2025-03-02 | 2025-03-15 | 9 | Yes | 1
APT-0467 | Operations SLA Dashboard | Sprint 12 - 2025 | Ananya Rao | Critical | 3 | Done | 2025-06-12 | 2025-06-16 | 2025-06-16 | Product | Medium | 19 | 20 | None | 2025-06-08 | 2025-06-21 | 3 | No | 1
APT-0468 | Operations SLA Dashboard | Sprint 05 - 2025 | Neha Verma | Low | 1 | Done | 2025-03-02 | 2025-03-10 | 2025-03-12 | Engineering | Medium | 5 | 4 | UAT Feedback | 2025-03-02 | 2025-03-15 | 9 | Yes | 1
APT-0469 | Backlog Prioritization Framework | Sprint 01 - 2025 | Kabir Khan | Critical | 3 | Done | 2025-01-13 | 2025-01-23 | 2025-01-22 | Engineering | High | 17 | 24 | None | 2025-01-05 | 2025-01-18 | 8 | No | 1
APT-0470 | Customer Onboarding Automation | Sprint 01 - 2025 | Kabir Khan | Critical | 1 | Done | 2025-01-06 | 2025-01-15 | 2025-01-15 | Customer Success | Medium | 8 | 7 | None | 2025-01-05 | 2025-01-18 | 8 | No | 1
APT-0471 | Operations SLA Dashboard | Sprint 08 - 2025 | Isha Sharma | Low | 5 | Testing | 2025-04-15 | 2025-04-20 |  | Product | Medium | 22 | 19 | Requirement Change | 2025-04-13 | 2025-04-26 | 0 | Yes | 0
APT-0472 | API Reliability Upgrade | Sprint 04 - 2025 | Vikram Singh | High | 5 | In Progress | 2025-02-17 | 2025-02-23 |  | Data Analytics | Medium | 22 | 17 | Scope Clarification | 2025-02-16 | 2025-03-01 | 0 | Yes | 0
APT-0473 | Customer Onboarding Automation | Sprint 10 - 2025 | Dev Patel | High | 3 | Done | 2025-05-13 | 2025-05-16 | 2025-05-16 | Product | Medium | 19 | 21 | None | 2025-05-11 | 2025-05-24 | 2 | No | 1
APT-0474 | API Reliability Upgrade | Sprint 08 - 2025 | Sara Thomas | Critical | 8 | Testing | 2025-04-15 | 2025-04-18 |  | QA | Low | 42 | 37 | Resource Constraint | 2025-04-13 | 2025-04-26 | 0 | Yes | 0
APT-0475 | Backlog Prioritization Framework | Sprint 10 - 2025 | Rohan Gupta | Medium | 13 | Done | 2025-05-15 | 2025-05-20 | 2025-05-21 | Data Analytics | Medium | 53 | 51 | Environment Issue | 2025-05-11 | 2025-05-24 | 5 | Yes | 1
APT-0476 | Mobile Experience Improvements | Sprint 05 - 2025 | Aarav Mehta | High | 5 | Done | 2025-03-06 | 2025-03-11 | 2025-03-10 | Customer Success | Low | 20 | 19 | None | 2025-03-02 | 2025-03-15 | 3 | No | 1
APT-0477 | Sprint Reporting Hub | Sprint 07 - 2025 | Meera Nair | Low | 5 | Done | 2025-04-06 | 2025-04-11 | 2025-04-12 | QA | Low | 25 | 24 | Resource Constraint | 2025-03-30 | 2025-04-12 | 5 | Yes | 1
APT-0478 | API Reliability Upgrade | Sprint 07 - 2025 | Neha Verma | High | 5 | Done | 2025-04-05 | 2025-04-16 | 2025-04-14 | Product | Medium | 23 | 21 | None | 2025-03-30 | 2025-04-12 | 8 | No | 1
APT-0479 | API Reliability Upgrade | Sprint 10 - 2025 | Meera Nair | Medium | 5 | Done | 2025-05-11 | 2025-05-21 | 2025-05-19 | Customer Success | Medium | 24 | 22 | None | 2025-05-11 | 2025-05-24 | 7 | No | 1
APT-0480 | Billing Workflow Optimization | Sprint 02 - 2025 | Rohan Gupta | Medium | 1 | Testing | 2025-01-19 | 2025-01-28 |  | Data Analytics | Medium | 6 | 7 | UAT Feedback | 2025-01-19 | 2025-02-01 | 0 | Yes | 0
APT-0481 | Data Quality Remediation | Sprint 06 - 2025 | Vikram Singh | Medium | 3 | Done | 2025-03-23 | 2025-04-03 | 2025-04-03 | Operations | Low | 17 | 16 | None | 2025-03-16 | 2025-03-29 | 10 | No | 1
APT-0482 | API Reliability Upgrade | Sprint 10 - 2025 | Isha Sharma | Critical | 5 | Done | 2025-05-17 | 2025-05-24 | 2025-05-26 | Customer Success | Medium | 24 | 27 | Environment Issue | 2025-05-11 | 2025-05-24 | 8 | Yes | 1
APT-0483 | Customer Onboarding Automation | Sprint 09 - 2025 | Sara Thomas | Low | 2 | Testing | 2025-05-04 | 2025-05-15 |  | Customer Success | Low | 9 | 8 | Dependency Blocker | 2025-04-27 | 2025-05-10 | 0 | Yes | 0
APT-0484 | Stakeholder Notification Service | Sprint 02 - 2025 | Aarav Mehta | Medium | 8 | Testing | 2025-01-19 | 2025-01-29 |  | Operations | Low | 41 | 39 | UAT Feedback | 2025-01-19 | 2025-02-01 | 0 | Yes | 0
APT-0485 | Stakeholder Notification Service | Sprint 08 - 2025 | Vikram Singh | Medium | 3 | Done | 2025-04-17 | 2025-04-25 | 2025-04-23 | Data Analytics | High | 15 | 17 | None | 2025-04-13 | 2025-04-26 | 5 | No | 1
APT-0486 | Backlog Prioritization Framework | Sprint 12 - 2025 | Ananya Rao | High | 1 | In Progress | 2025-06-12 | 2025-06-18 |  | Engineering | Low | 6 | 5 | Requirement Change | 2025-06-08 | 2025-06-21 | 0 | Yes | 0
APT-0487 | User Access Governance | Sprint 06 - 2025 | Vikram Singh | Medium | 5 | Done | 2025-03-20 | 2025-03-27 | 2025-03-29 | Operations | Medium | 22 | 28 | Requirement Change | 2025-03-16 | 2025-03-29 | 8 | Yes | 1
APT-0488 | Customer Onboarding Automation | Sprint 06 - 2025 | Rohan Gupta | Medium | 5 | Done | 2025-03-17 | 2025-03-29 | 2025-03-30 | Product | High | 27 | 29 | Requirement Change | 2025-03-16 | 2025-03-29 | 12 | Yes | 1
APT-0489 | Data Quality Remediation | Sprint 11 - 2025 | Zoya Fernandes | Critical | 3 | Done | 2025-05-27 | 2025-06-05 | 2025-06-06 | Customer Success | High | 28 | 40 | Scope Clarification | 2025-05-25 | 2025-06-07 | 9 | Yes | 1
APT-0490 | Billing Workflow Optimization | Sprint 03 - 2025 | Arjun Menon | High | 8 | Done | 2025-02-07 | 2025-02-15 | 2025-02-15 | Operations | High | 51 | 56 | None | 2025-02-02 | 2025-02-15 | 7 | No | 1
APT-0491 | API Reliability Upgrade | Sprint 11 - 2025 | Neha Verma | Critical | 8 | Done | 2025-05-25 | 2025-05-29 | 2025-05-27 | QA | Medium | 60 | 66 | None | 2025-05-25 | 2025-06-07 | 1 | No | 1
APT-0492 | Data Quality Remediation | Sprint 04 - 2025 | Zoya Fernandes | High | 5 | Done | 2025-02-18 | 2025-03-01 | 2025-02-27 | Data Analytics | Medium | 34 | 41 | None | 2025-02-16 | 2025-03-01 | 8 | No | 1
APT-0493 | Data Quality Remediation | Sprint 06 - 2025 | Sara Thomas | Medium | 2 | Done | 2025-03-21 | 2025-03-29 | 2025-03-29 | Customer Success | Low | 8 | 7 | None | 2025-03-16 | 2025-03-29 | 7 | No | 1
APT-0494 | Data Quality Remediation | Sprint 11 - 2025 | Kabir Khan | High | 2 | Done | 2025-06-02 | 2025-06-09 | 2025-06-11 | Customer Success | Medium | 11 | 13 | Environment Issue | 2025-05-25 | 2025-06-07 | 8 | Yes | 1
APT-0495 | Stakeholder Notification Service | Sprint 06 - 2025 | Zoya Fernandes | Medium | 1 | Done | 2025-03-24 | 2025-03-31 | 2025-04-05 | Customer Success | High | 7 | 8 | Scope Clarification | 2025-03-16 | 2025-03-29 | 11 | Yes | 1
APT-0496 | Mobile Experience Improvements | Sprint 08 - 2025 | Kabir Khan | Critical | 3 | Done | 2025-04-13 | 2025-04-21 | 2025-04-19 | Engineering | Medium | 15 | 21 | None | 2025-04-13 | 2025-04-26 | 5 | No | 1
APT-0497 | Billing Workflow Optimization | Sprint 08 - 2025 | Vikram Singh | High | 1 | In Progress | 2025-04-19 | 2025-04-30 |  | QA | Low | 6 | 3 | Dependency Blocker | 2025-04-13 | 2025-04-26 | 0 | Yes | 0
APT-0498 | User Access Governance | Sprint 06 - 2025 | Rohan Gupta | High | 8 | Done | 2025-03-17 | 2025-03-22 | 2025-03-23 | Engineering | Medium | 32 | 30 | UAT Feedback | 2025-03-16 | 2025-03-29 | 5 | Yes | 1
APT-0499 | Billing Workflow Optimization | Sprint 07 - 2025 | Ananya Rao | High | 5 | Done | 2025-04-03 | 2025-04-07 | 2025-04-09 | Engineering | Medium | 23 | 31 | Resource Constraint | 2025-03-30 | 2025-04-12 | 5 | Yes | 1
APT-0500 | User Access Governance | Sprint 02 - 2025 | Sara Thomas | Low | 2 | Testing | 2025-01-27 | 2025-02-02 |  | Engineering | Low | 6 | 6 | Scope Clarification | 2025-01-19 | 2025-02-01 | 0 | Yes | 0
APT-0501 | Billing Workflow Optimization | Sprint 03 - 2025 | Aarav Mehta | High | 3 | Done | 2025-02-02 | 2025-02-14 | 2025-02-14 | Product | Low | 12 | 10 | None | 2025-02-02 | 2025-02-15 | 11 | No | 1
APT-0502 | API Reliability Upgrade | Sprint 01 - 2025 | Dev Patel | Low | 8 | Done | 2025-01-07 | 2025-01-12 | 2025-01-12 | Engineering | Low | 43 | 53 | None | 2025-01-05 | 2025-01-18 | 4 | No | 1
APT-0503 | API Reliability Upgrade | Sprint 01 - 2025 | Neha Verma | Medium | 5 | Testing | 2025-01-10 | 2025-01-21 |  | Engineering | Low | 24 | 18 | Resource Constraint | 2025-01-05 | 2025-01-18 | 0 | Yes | 0
APT-0504 | Data Quality Remediation | Sprint 03 - 2025 | Neha Verma | Medium | 1 | Done | 2025-02-10 | 2025-02-20 | 2025-02-20 | Data Analytics | Low | 5 | 6 | None | 2025-02-02 | 2025-02-15 | 9 | No | 1
APT-0505 | Backlog Prioritization Framework | Sprint 05 - 2025 | Zoya Fernandes | Medium | 3 | Done | 2025-03-06 | 2025-03-13 | 2025-03-14 | Product | Medium | 12 | 15 | Environment Issue | 2025-03-02 | 2025-03-15 | 7 | Yes | 1
APT-0506 | Sprint Reporting Hub | Sprint 11 - 2025 | Zoya Fernandes | Low | 3 | Testing | 2025-05-27 | 2025-06-05 |  | Data Analytics | High | 22 | 20 | Scope Clarification | 2025-05-25 | 2025-06-07 | 0 | Yes | 0
APT-0507 | Backlog Prioritization Framework | Sprint 10 - 2025 | Kabir Khan | High | 3 | Done | 2025-05-15 | 2025-05-21 | 2025-05-22 | Product | Low | 14 | 13 | Resource Constraint | 2025-05-11 | 2025-05-24 | 6 | Yes | 1
APT-0508 | Backlog Prioritization Framework | Sprint 01 - 2025 | Dev Patel | High | 3 | In Progress | 2025-01-13 | 2025-01-19 |  | Customer Success | Low | 17 | 10 | Environment Issue | 2025-01-05 | 2025-01-18 | 0 | Yes | 0
APT-0509 | Stakeholder Notification Service | Sprint 07 - 2025 | Ananya Rao | High | 3 | Done | 2025-04-06 | 2025-04-09 | 2025-04-09 | Engineering | Low | 11 | 9 | None | 2025-03-30 | 2025-04-12 | 2 | No | 1
APT-0510 | Mobile Experience Improvements | Sprint 04 - 2025 | Meera Nair | High | 8 | Done | 2025-02-23 | 2025-03-06 | 2025-03-06 | Data Analytics | Low | 34 | 28 | None | 2025-02-16 | 2025-03-01 | 10 | No | 1
APT-0511 | API Reliability Upgrade | Sprint 11 - 2025 | Rohan Gupta | Low | 3 | In Progress | 2025-05-29 | 2025-06-06 |  | QA | Low | 12 | 8 | Dependency Blocker | 2025-05-25 | 2025-06-07 | 0 | Yes | 0
APT-0512 | Billing Workflow Optimization | Sprint 09 - 2025 | Vikram Singh | Medium | 1 | Done | 2025-05-05 | 2025-05-13 | 2025-05-16 | Data Analytics | Medium | 6 | 6 | Requirement Change | 2025-04-27 | 2025-05-10 | 10 | Yes | 1
APT-0513 | User Access Governance | Sprint 04 - 2025 | Zoya Fernandes | High | 3 | Done | 2025-02-17 | 2025-02-27 | 2025-03-01 | Operations | Medium | 18 | 20 | Scope Clarification | 2025-02-16 | 2025-03-01 | 11 | Yes | 1
APT-0514 | Sprint Reporting Hub | Sprint 01 - 2025 | Kabir Khan | Medium | 3 | Done | 2025-01-08 | 2025-01-11 | 2025-01-09 | Customer Success | High | 22 | 32 | None | 2025-01-05 | 2025-01-18 | 1 | No | 1
APT-0515 | Operations SLA Dashboard | Sprint 12 - 2025 | Meera Nair | Medium | 3 | Testing | 2025-06-15 | 2025-06-25 |  | Data Analytics | Medium | 14 | 15 | Requirement Change | 2025-06-08 | 2025-06-21 | 0 | Yes | 0
APT-0516 | Operations SLA Dashboard | Sprint 02 - 2025 | Ananya Rao | Medium | 1 | Testing | 2025-01-23 | 2025-01-31 |  | Product | Low | 4 | 4 | Environment Issue | 2025-01-19 | 2025-02-01 | 0 | Yes | 0
APT-0517 | Billing Workflow Optimization | Sprint 10 - 2025 | Isha Sharma | Medium | 1 | Done | 2025-05-11 | 2025-05-22 | 2025-05-24 | Product | Medium | 4 | 5 | Environment Issue | 2025-05-11 | 2025-05-24 | 12 | Yes | 1
APT-0518 | API Reliability Upgrade | Sprint 09 - 2025 | Arjun Menon | Medium | 5 | To Do | 2025-05-03 | 2025-05-10 |  | Data Analytics | Low | 20 | 0 | Environment Issue | 2025-04-27 | 2025-05-10 | 0 | Yes | 0
APT-0519 | Stakeholder Notification Service | Sprint 08 - 2025 | Kabir Khan | Critical | 5 | Done | 2025-04-16 | 2025-04-24 | 2025-04-22 | Customer Success | Medium | 36 | 41 | None | 2025-04-13 | 2025-04-26 | 5 | No | 1
APT-0520 | Customer Onboarding Automation | Sprint 06 - 2025 | Meera Nair | High | 8 | Done | 2025-03-21 | 2025-03-28 | 2025-03-28 | Data Analytics | Low | 44 | 43 | None | 2025-03-16 | 2025-03-29 | 6 | No | 1
APT-0521 | Operations SLA Dashboard | Sprint 05 - 2025 | Dev Patel | Medium | 2 | Done | 2025-03-08 | 2025-03-11 | 2025-03-09 | Product | Low | 12 | 13 | None | 2025-03-02 | 2025-03-15 | 1 | No | 1
APT-0522 | Mobile Experience Improvements | Sprint 12 - 2025 | Sara Thomas | Critical | 2 | In Progress | 2025-06-15 | 2025-06-25 |  | Data Analytics | Low | 8 | 6 | Resource Constraint | 2025-06-08 | 2025-06-21 | 0 | Yes | 0
APT-0523 | User Access Governance | Sprint 07 - 2025 | Ananya Rao | Critical | 8 | Done | 2025-04-03 | 2025-04-14 | 2025-04-12 | Customer Success | Low | 46 | 54 | None | 2025-03-30 | 2025-04-12 | 8 | No | 1
APT-0524 | Data Quality Remediation | Sprint 10 - 2025 | Vikram Singh | High | 8 | Done | 2025-05-16 | 2025-05-28 | 2025-05-28 | Customer Success | High | 63 | 86 | None | 2025-05-11 | 2025-05-24 | 11 | No | 1
APT-0525 | Customer Onboarding Automation | Sprint 02 - 2025 | Isha Sharma | Low | 3 | Done | 2025-01-25 | 2025-01-31 | 2025-02-01 | Customer Success | Medium | 11 | 14 | Resource Constraint | 2025-01-19 | 2025-02-01 | 6 | Yes | 1
APT-0526 | Backlog Prioritization Framework | Sprint 07 - 2025 | Vikram Singh | Critical | 5 | Done | 2025-04-04 | 2025-04-13 | 2025-04-11 | Operations | Medium | 33 | 41 | None | 2025-03-30 | 2025-04-12 | 6 | No | 1
APT-0527 | Customer Onboarding Automation | Sprint 03 - 2025 | Rohan Gupta | Critical | 5 | Done | 2025-02-04 | 2025-02-08 | 2025-02-10 | Product | High | 39 | 43 | Environment Issue | 2025-02-02 | 2025-02-15 | 5 | Yes | 1
APT-0528 | User Access Governance | Sprint 09 - 2025 | Vikram Singh | Medium | 2 | To Do | 2025-04-27 | 2025-05-04 |  | Product | Medium | 11 | 0 | Dependency Blocker | 2025-04-27 | 2025-05-10 | 0 | Yes | 0
APT-0529 | Mobile Experience Improvements | Sprint 04 - 2025 | Arjun Menon | Medium | 3 | Done | 2025-02-18 | 2025-02-21 | 2025-02-23 | Engineering | Medium | 13 | 12 | Dependency Blocker | 2025-02-16 | 2025-03-01 | 4 | Yes | 1
APT-0530 | Operations SLA Dashboard | Sprint 11 - 2025 | Arjun Menon | Medium | 3 | Done | 2025-05-27 | 2025-06-08 | 2025-06-08 | Product | Low | 17 | 18 | None | 2025-05-25 | 2025-06-07 | 11 | No | 1
APT-0531 | Data Quality Remediation | Sprint 09 - 2025 | Zoya Fernandes | Critical | 3 | Done | 2025-04-30 | 2025-05-07 | 2025-05-06 | Customer Success | High | 17 | 24 | None | 2025-04-27 | 2025-05-10 | 5 | No | 1
APT-0532 | Data Quality Remediation | Sprint 07 - 2025 | Meera Nair | Critical | 3 | Done | 2025-04-07 | 2025-04-17 | 2025-04-16 | Operations | Low | 12 | 13 | None | 2025-03-30 | 2025-04-12 | 8 | No | 1
APT-0533 | Billing Workflow Optimization | Sprint 01 - 2025 | Neha Verma | Low | 3 | Testing | 2025-01-09 | 2025-01-15 |  | QA | Medium | 16 | 17 | Dependency Blocker | 2025-01-05 | 2025-01-18 | 0 | Yes | 0
APT-0534 | Sprint Reporting Hub | Sprint 04 - 2025 | Meera Nair | Low | 2 | Done | 2025-02-22 | 2025-03-03 | 2025-03-04 | Product | Low | 7 | 8 | Requirement Change | 2025-02-16 | 2025-03-01 | 9 | Yes | 1
APT-0535 | Mobile Experience Improvements | Sprint 11 - 2025 | Rohan Gupta | High | 2 | Testing | 2025-05-25 | 2025-05-29 |  | Data Analytics | Medium | 9 | 8 | Scope Clarification | 2025-05-25 | 2025-06-07 | 0 | Yes | 0
APT-0536 | Billing Workflow Optimization | Sprint 11 - 2025 | Dev Patel | Low | 3 | Testing | 2025-05-26 | 2025-05-29 |  | Product | Medium | 19 | 19 | Requirement Change | 2025-05-25 | 2025-06-07 | 0 | Yes | 0
APT-0537 | Stakeholder Notification Service | Sprint 09 - 2025 | Dev Patel | High | 3 | Done | 2025-05-04 | 2025-05-12 | 2025-05-13 | Operations | Medium | 12 | 13 | Requirement Change | 2025-04-27 | 2025-05-10 | 8 | Yes | 1
APT-0538 | Sprint Reporting Hub | Sprint 07 - 2025 | Meera Nair | Medium | 5 | In Progress | 2025-04-07 | 2025-04-12 |  | Customer Success | High | 34 | 26 | Environment Issue | 2025-03-30 | 2025-04-12 | 0 | Yes | 0
APT-0539 | Sprint Reporting Hub | Sprint 09 - 2025 | Isha Sharma | Medium | 1 | Testing | 2025-04-28 | 2025-05-06 |  | Customer Success | Low | 4 | 3 | Dependency Blocker | 2025-04-27 | 2025-05-10 | 0 | Yes | 0
APT-0540 | Backlog Prioritization Framework | Sprint 10 - 2025 | Zoya Fernandes | Low | 1 | Done | 2025-05-13 | 2025-05-21 | 2025-05-22 | Operations | Low | 5 | 6 | Resource Constraint | 2025-05-11 | 2025-05-24 | 8 | Yes | 1
APT-0541 | Customer Onboarding Automation | Sprint 07 - 2025 | Vikram Singh | Medium | 3 | Done | 2025-04-06 | 2025-04-10 | 2025-04-10 | Operations | High | 20 | 28 | None | 2025-03-30 | 2025-04-12 | 3 | No | 1
APT-0542 | API Reliability Upgrade | Sprint 01 - 2025 | Kabir Khan | High | 8 | Done | 2025-01-06 | 2025-01-17 | 2025-01-17 | Product | Low | 43 | 42 | None | 2025-01-05 | 2025-01-18 | 10 | No | 1
APT-0543 | User Access Governance | Sprint 08 - 2025 | Neha Verma | High | 1 | Done | 2025-04-13 | 2025-04-22 | 2025-04-21 | Product | Low | 6 | 7 | None | 2025-04-13 | 2025-04-26 | 7 | No | 1
APT-0544 | Billing Workflow Optimization | Sprint 02 - 2025 | Vikram Singh | Low | 5 | Done | 2025-01-19 | 2025-01-24 | 2025-01-22 | Data Analytics | Low | 19 | 21 | None | 2025-01-19 | 2025-02-01 | 2 | No | 1
APT-0545 | Mobile Experience Improvements | Sprint 02 - 2025 | Neha Verma | Medium | 3 | In Progress | 2025-01-22 | 2025-02-02 |  | Product | Low | 17 | 11 | UAT Feedback | 2025-01-19 | 2025-02-01 | 0 | Yes | 0
APT-0546 | User Access Governance | Sprint 03 - 2025 | Rohan Gupta | Medium | 3 | Done | 2025-02-05 | 2025-02-12 | 2025-02-14 | Product | Medium | 19 | 23 | UAT Feedback | 2025-02-02 | 2025-02-15 | 8 | Yes | 1
APT-0547 | Data Quality Remediation | Sprint 08 - 2025 | Zoya Fernandes | Low | 5 | Done | 2025-04-21 | 2025-04-28 | 2025-04-26 | Customer Success | Low | 23 | 19 | None | 2025-04-13 | 2025-04-26 | 4 | No | 1
APT-0548 | Mobile Experience Improvements | Sprint 04 - 2025 | Rohan Gupta | Low | 3 | To Do | 2025-02-21 | 2025-03-01 |  | QA | Medium | 13 | 0 | UAT Feedback | 2025-02-16 | 2025-03-01 | 0 | Yes | 0
APT-0549 | Customer Onboarding Automation | Sprint 04 - 2025 | Meera Nair | High | 3 | Done | 2025-02-17 | 2025-02-22 | 2025-02-22 | Data Analytics | Low | 18 | 15 | None | 2025-02-16 | 2025-03-01 | 4 | No | 1
APT-0550 | Data Quality Remediation | Sprint 01 - 2025 | Sara Thomas | Medium | 5 | In Progress | 2025-01-13 | 2025-01-21 |  | Product | Low | 27 | 16 | Scope Clarification | 2025-01-05 | 2025-01-18 | 0 | Yes | 0
APT-0551 | Data Quality Remediation | Sprint 06 - 2025 | Zoya Fernandes | High | 5 | Done | 2025-03-17 | 2025-03-23 | 2025-03-23 | Operations | Medium | 20 | 23 | None | 2025-03-16 | 2025-03-29 | 5 | No | 1
APT-0552 | API Reliability Upgrade | Sprint 01 - 2025 | Kabir Khan | Medium | 8 | Done | 2025-01-12 | 2025-01-22 | 2025-01-24 | Product | Low | 37 | 30 | Resource Constraint | 2025-01-05 | 2025-01-18 | 11 | Yes | 1
APT-0553 | API Reliability Upgrade | Sprint 03 - 2025 | Kabir Khan | High | 1 | Done | 2025-02-02 | 2025-02-05 | 2025-02-05 | Operations | Medium | 4 | 4 | None | 2025-02-02 | 2025-02-15 | 2 | No | 1
APT-0554 | Mobile Experience Improvements | Sprint 08 - 2025 | Ananya Rao | Medium | 5 | To Do | 2025-04-16 | 2025-04-23 |  | Customer Success | Medium | 29 | 0 | Resource Constraint | 2025-04-13 | 2025-04-26 | 0 | Yes | 0
APT-0555 | Customer Onboarding Automation | Sprint 03 - 2025 | Zoya Fernandes | Low | 2 | Done | 2025-02-07 | 2025-02-11 | 2025-02-11 | Engineering | Low | 8 | 8 | None | 2025-02-02 | 2025-02-15 | 3 | No | 1
APT-0556 | Billing Workflow Optimization | Sprint 01 - 2025 | Vikram Singh | Low | 3 | Done | 2025-01-09 | 2025-01-12 | 2025-01-12 | Customer Success | High | 18 | 23 | None | 2025-01-05 | 2025-01-18 | 2 | No | 1
APT-0557 | Customer Onboarding Automation | Sprint 07 - 2025 | Aarav Mehta | High | 3 | Done | 2025-04-05 | 2025-04-13 | 2025-04-13 | Product | Low | 12 | 12 | None | 2025-03-30 | 2025-04-12 | 7 | No | 1
APT-0558 | API Reliability Upgrade | Sprint 09 - 2025 | Zoya Fernandes | Medium | 3 | Done | 2025-05-04 | 2025-05-11 | 2025-05-11 | Product | High | 18 | 24 | None | 2025-04-27 | 2025-05-10 | 6 | No | 1
APT-0559 | Customer Onboarding Automation | Sprint 09 - 2025 | Rohan Gupta | High | 8 | To Do | 2025-05-05 | 2025-05-12 |  | Product | Medium | 50 | 0 | Requirement Change | 2025-04-27 | 2025-05-10 | 0 | Yes | 0
APT-0560 | Backlog Prioritization Framework | Sprint 12 - 2025 | Meera Nair | High | 2 | Done | 2025-06-11 | 2025-06-22 | 2025-06-24 | Data Analytics | High | 15 | 18 | Resource Constraint | 2025-06-08 | 2025-06-21 | 12 | Yes | 1
APT-0561 | Stakeholder Notification Service | Sprint 12 - 2025 | Arjun Menon | Low | 1 | Done | 2025-06-16 | 2025-06-24 | 2025-06-22 | Data Analytics | Medium | 4 | 5 | None | 2025-06-08 | 2025-06-21 | 5 | No | 1
APT-0562 | Data Quality Remediation | Sprint 08 - 2025 | Kabir Khan | High | 5 | In Progress | 2025-04-17 | 2025-04-22 |  | QA | Low | 28 | 10 | Requirement Change | 2025-04-13 | 2025-04-26 | 0 | Yes | 0
APT-0563 | Stakeholder Notification Service | Sprint 03 - 2025 | Vikram Singh | Medium | 3 | Done | 2025-02-04 | 2025-02-10 | 2025-02-10 | Engineering | Low | 17 | 17 | None | 2025-02-02 | 2025-02-15 | 5 | No | 1
APT-0564 | Backlog Prioritization Framework | Sprint 06 - 2025 | Arjun Menon | Medium | 5 | Done | 2025-03-16 | 2025-03-26 | 2025-03-26 | Engineering | Low | 26 | 32 | None | 2025-03-16 | 2025-03-29 | 9 | No | 1
APT-0565 | Backlog Prioritization Framework | Sprint 11 - 2025 | Vikram Singh | High | 3 | Done | 2025-05-25 | 2025-06-04 | 2025-06-04 | Operations | Low | 13 | 12 | None | 2025-05-25 | 2025-06-07 | 9 | No | 1
APT-0566 | User Access Governance | Sprint 04 - 2025 | Rohan Gupta | Critical | 2 | Done | 2025-02-20 | 2025-02-24 | 2025-02-22 | Engineering | High | 16 | 19 | None | 2025-02-16 | 2025-03-01 | 1 | No | 1
APT-0567 | Billing Workflow Optimization | Sprint 10 - 2025 | Vikram Singh | High | 1 | Done | 2025-05-18 | 2025-05-29 | 2025-05-29 | Customer Success | Low | 6 | 7 | None | 2025-05-11 | 2025-05-24 | 10 | No | 1
APT-0568 | Billing Workflow Optimization | Sprint 08 - 2025 | Zoya Fernandes | Medium | 8 | In Progress | 2025-04-20 | 2025-04-26 |  | Product | High | 49 | 46 | UAT Feedback | 2025-04-13 | 2025-04-26 | 0 | Yes | 0
APT-0569 | Billing Workflow Optimization | Sprint 06 - 2025 | Sara Thomas | Low | 3 | Done | 2025-03-22 | 2025-03-28 | 2025-03-28 | QA | High | 20 | 28 | None | 2025-03-16 | 2025-03-29 | 5 | No | 1
APT-0570 | API Reliability Upgrade | Sprint 09 - 2025 | Rohan Gupta | High | 5 | Done | 2025-04-30 | 2025-05-10 | 2025-05-11 | QA | High | 24 | 37 | Resource Constraint | 2025-04-27 | 2025-05-10 | 10 | Yes | 1
APT-0571 | Data Quality Remediation | Sprint 07 - 2025 | Zoya Fernandes | Medium | 5 | Testing | 2025-04-06 | 2025-04-12 |  | Data Analytics | High | 22 | 21 | Requirement Change | 2025-03-30 | 2025-04-12 | 0 | Yes | 0
APT-0572 | API Reliability Upgrade | Sprint 01 - 2025 | Aarav Mehta | Low | 5 | Done | 2025-01-12 | 2025-01-19 | 2025-01-20 | Customer Success | Medium | 31 | 38 | UAT Feedback | 2025-01-05 | 2025-01-18 | 7 | Yes | 1
APT-0573 | Billing Workflow Optimization | Sprint 04 - 2025 | Rohan Gupta | Critical | 8 | Done | 2025-02-22 | 2025-03-04 | 2025-03-03 | Engineering | High | 50 | 72 | None | 2025-02-16 | 2025-03-01 | 8 | No | 1
APT-0574 | Sprint Reporting Hub | Sprint 05 - 2025 | Kabir Khan | High | 5 | To Do | 2025-03-10 | 2025-03-15 |  | Data Analytics | Medium | 32 | 0 | Environment Issue | 2025-03-02 | 2025-03-15 | 0 | Yes | 0
APT-0575 | Sprint Reporting Hub | Sprint 10 - 2025 | Zoya Fernandes | High | 8 | Done | 2025-05-11 | 2025-05-19 | 2025-05-19 | Engineering | Medium | 42 | 47 | None | 2025-05-11 | 2025-05-24 | 7 | No | 1
APT-0576 | Sprint Reporting Hub | Sprint 05 - 2025 | Rohan Gupta | Medium | 3 | Done | 2025-03-10 | 2025-03-17 | 2025-03-16 | Product | Low | 10 | 10 | None | 2025-03-02 | 2025-03-15 | 5 | No | 1
APT-0577 | Customer Onboarding Automation | Sprint 03 - 2025 | Meera Nair | Low | 2 | Done | 2025-02-06 | 2025-02-18 | 2025-02-20 | QA | High | 9 | 10 | Scope Clarification | 2025-02-02 | 2025-02-15 | 13 | Yes | 1
APT-0578 | Backlog Prioritization Framework | Sprint 04 - 2025 | Vikram Singh | Medium | 8 | Done | 2025-02-20 | 2025-02-27 | 2025-03-05 | Engineering | High | 44 | 65 | Requirement Change | 2025-02-16 | 2025-03-01 | 12 | Yes | 1
APT-0579 | User Access Governance | Sprint 03 - 2025 | Dev Patel | High | 3 | Done | 2025-02-03 | 2025-02-14 | 2025-02-12 | Data Analytics | Low | 19 | 18 | None | 2025-02-02 | 2025-02-15 | 8 | No | 1
APT-0580 | Billing Workflow Optimization | Sprint 12 - 2025 | Dev Patel | Medium | 1 | Done | 2025-06-10 | 2025-06-15 | 2025-06-14 | Engineering | Medium | 4 | 5 | None | 2025-06-08 | 2025-06-21 | 3 | No | 1
APT-0581 | API Reliability Upgrade | Sprint 10 - 2025 | Zoya Fernandes | Medium | 2 | Done | 2025-05-11 | 2025-05-14 | 2025-05-13 | Customer Success | Low | 10 | 12 | None | 2025-05-11 | 2025-05-24 | 1 | No | 1
APT-0582 | Billing Workflow Optimization | Sprint 02 - 2025 | Aarav Mehta | Low | 1 | Done | 2025-01-27 | 2025-02-06 | 2025-02-08 | Customer Success | Low | 6 | 6 | Environment Issue | 2025-01-19 | 2025-02-01 | 11 | Yes | 1
APT-0583 | Sprint Reporting Hub | Sprint 07 - 2025 | Meera Nair | Medium | 3 | In Progress | 2025-04-01 | 2025-04-06 |  | Engineering | Low | 15 | 8 | Scope Clarification | 2025-03-30 | 2025-04-12 | 0 | Yes | 0
APT-0584 | Customer Onboarding Automation | Sprint 08 - 2025 | Neha Verma | High | 8 | Done | 2025-04-16 | 2025-04-26 | 2025-04-26 | Engineering | Medium | 56 | 66 | None | 2025-04-13 | 2025-04-26 | 9 | No | 1
APT-0585 | Mobile Experience Improvements | Sprint 02 - 2025 | Meera Nair | High | 2 | Done | 2025-01-21 | 2025-02-02 | 2025-02-04 | QA | Low | 13 | 12 | Resource Constraint | 2025-01-19 | 2025-02-01 | 13 | Yes | 1
APT-0586 | Sprint Reporting Hub | Sprint 05 - 2025 | Sara Thomas | Medium | 2 | Done | 2025-03-04 | 2025-03-15 | 2025-03-15 | Operations | Low | 11 | 13 | None | 2025-03-02 | 2025-03-15 | 10 | No | 1
APT-0587 | Operations SLA Dashboard | Sprint 04 - 2025 | Dev Patel | High | 8 | Done | 2025-02-18 | 2025-02-21 | 2025-02-22 | Product | Medium | 42 | 56 | Requirement Change | 2025-02-16 | 2025-03-01 | 3 | Yes | 1
APT-0588 | Customer Onboarding Automation | Sprint 04 - 2025 | Dev Patel | Medium | 3 | Done | 2025-02-16 | 2025-02-28 | 2025-02-28 | QA | Medium | 14 | 16 | None | 2025-02-16 | 2025-03-01 | 11 | No | 1
APT-0589 | Sprint Reporting Hub | Sprint 06 - 2025 | Aarav Mehta | Medium | 2 | Done | 2025-03-20 | 2025-03-29 | 2025-03-30 | Engineering | Medium | 8 | 11 | Environment Issue | 2025-03-16 | 2025-03-29 | 9 | Yes | 1
APT-0590 | Customer Onboarding Automation | Sprint 12 - 2025 | Zoya Fernandes | High | 3 | To Do | 2025-06-10 | 2025-06-18 |  | Engineering | Low | 15 | 0 | UAT Feedback | 2025-06-08 | 2025-06-21 | 0 | Yes | 0
APT-0591 | Mobile Experience Improvements | Sprint 06 - 2025 | Ananya Rao | Medium | 8 | Done | 2025-03-20 | 2025-03-27 | 2025-03-27 | Engineering | Low | 43 | 46 | None | 2025-03-16 | 2025-03-29 | 6 | No | 1
APT-0592 | Sprint Reporting Hub | Sprint 08 - 2025 | Meera Nair | Low | 1 | In Progress | 2025-04-19 | 2025-04-24 |  | Data Analytics | Medium | 4 | 2 | Resource Constraint | 2025-04-13 | 2025-04-26 | 0 | Yes | 0
APT-0593 | Mobile Experience Improvements | Sprint 11 - 2025 | Zoya Fernandes | Low | 5 | Testing | 2025-05-31 | 2025-06-07 |  | Customer Success | Medium | 29 | 29 | Resource Constraint | 2025-05-25 | 2025-06-07 | 0 | Yes | 0
APT-0594 | Customer Onboarding Automation | Sprint 07 - 2025 | Arjun Menon | Medium | 8 | Done | 2025-04-01 | 2025-04-10 | 2025-04-10 | Product | Low | 34 | 31 | None | 2025-03-30 | 2025-04-12 | 8 | No | 1
APT-0595 | Billing Workflow Optimization | Sprint 04 - 2025 | Isha Sharma | High | 5 | Done | 2025-02-22 | 2025-02-26 | 2025-02-26 | Operations | Medium | 32 | 34 | None | 2025-02-16 | 2025-03-01 | 3 | No | 1
APT-0596 | Stakeholder Notification Service | Sprint 10 - 2025 | Kabir Khan | High | 3 | Done | 2025-05-13 | 2025-05-23 | 2025-05-23 | QA | Low | 14 | 13 | None | 2025-05-11 | 2025-05-24 | 9 | No | 1
APT-0597 | API Reliability Upgrade | Sprint 05 - 2025 | Vikram Singh | Critical | 5 | Done | 2025-03-06 | 2025-03-09 | 2025-03-12 | QA | Medium | 25 | 34 | Requirement Change | 2025-03-02 | 2025-03-15 | 5 | Yes | 1
APT-0598 | Data Quality Remediation | Sprint 03 - 2025 | Neha Verma | Low | 3 | Done | 2025-02-04 | 2025-02-07 | 2025-02-08 | Data Analytics | Low | 9 | 10 | Scope Clarification | 2025-02-02 | 2025-02-15 | 3 | Yes | 1
APT-0599 | Customer Onboarding Automation | Sprint 07 - 2025 | Neha Verma | High | 5 | Done | 2025-03-31 | 2025-04-11 | 2025-04-11 | Data Analytics | Low | 32 | 33 | None | 2025-03-30 | 2025-04-12 | 10 | No | 1
APT-0600 | Billing Workflow Optimization | Sprint 04 - 2025 | Neha Verma | Medium | 1 | Testing | 2025-02-23 | 2025-02-28 |  | QA | Low | 4 | 3 | Requirement Change | 2025-02-16 | 2025-03-01 | 0 | Yes | 0
APT-0601 | Data Quality Remediation | Sprint 11 - 2025 | Sara Thomas | High | 13 | In Progress | 2025-06-02 | 2025-06-05 |  | Product | Low | 51 | 23 | Dependency Blocker | 2025-05-25 | 2025-06-07 | 0 | Yes | 0
APT-0602 | Operations SLA Dashboard | Sprint 02 - 2025 | Sara Thomas | High | 8 | Done | 2025-01-22 | 2025-01-26 | 2025-01-28 | Data Analytics | High | 51 | 78 | Resource Constraint | 2025-01-19 | 2025-02-01 | 5 | Yes | 1
APT-0603 | Backlog Prioritization Framework | Sprint 07 - 2025 | Kabir Khan | Medium | 5 | Done | 2025-04-04 | 2025-04-16 | 2025-04-18 | Product | Low | 25 | 28 | Resource Constraint | 2025-03-30 | 2025-04-12 | 13 | Yes | 1
APT-0604 | Billing Workflow Optimization | Sprint 06 - 2025 | Rohan Gupta | Low | 3 | Testing | 2025-03-24 | 2025-03-30 |  | Customer Success | Low | 16 | 12 | Requirement Change | 2025-03-16 | 2025-03-29 | 0 | Yes | 0
APT-0605 | Data Quality Remediation | Sprint 03 - 2025 | Rohan Gupta | Medium | 2 | Done | 2025-02-09 | 2025-02-20 | 2025-02-18 | Product | Low | 11 | 11 | None | 2025-02-02 | 2025-02-15 | 8 | No | 1
APT-0606 | Sprint Reporting Hub | Sprint 05 - 2025 | Neha Verma | Critical | 1 | Done | 2025-03-04 | 2025-03-11 | 2025-03-11 | Engineering | High | 6 | 9 | None | 2025-03-02 | 2025-03-15 | 6 | No | 1
APT-0607 | Customer Onboarding Automation | Sprint 05 - 2025 | Arjun Menon | Medium | 1 | Done | 2025-03-02 | 2025-03-11 | 2025-03-09 | Data Analytics | Low | 6 | 6 | None | 2025-03-02 | 2025-03-15 | 6 | No | 1
APT-0608 | Data Quality Remediation | Sprint 11 - 2025 | Sara Thomas | Medium | 2 | Done | 2025-05-30 | 2025-06-06 | 2025-06-06 | Data Analytics | Medium | 9 | 8 | None | 2025-05-25 | 2025-06-07 | 6 | No | 1
APT-0609 | Data Quality Remediation | Sprint 06 - 2025 | Meera Nair | Medium | 3 | Done | 2025-03-20 | 2025-03-26 | 2025-03-25 | Operations | High | 19 | 24 | None | 2025-03-16 | 2025-03-29 | 4 | No | 1
APT-0610 | Customer Onboarding Automation | Sprint 12 - 2025 | Rohan Gupta | Low | 2 | Done | 2025-06-16 | 2025-06-19 | 2025-06-18 | Operations | Low | 9 | 10 | None | 2025-06-08 | 2025-06-21 | 1 | No | 1
APT-0611 | Data Quality Remediation | Sprint 11 - 2025 | Isha Sharma | Medium | 3 | In Progress | 2025-05-26 | 2025-05-31 |  | Engineering | Medium | 19 | 14 | UAT Feedback | 2025-05-25 | 2025-06-07 | 0 | Yes | 0
APT-0612 | User Access Governance | Sprint 02 - 2025 | Zoya Fernandes | Low | 5 | Done | 2025-01-27 | 2025-02-02 | 2025-02-04 | Product | Low | 25 | 21 | Resource Constraint | 2025-01-19 | 2025-02-01 | 7 | Yes | 1
APT-0613 | Backlog Prioritization Framework | Sprint 10 - 2025 | Neha Verma | Low | 8 | Done | 2025-05-19 | 2025-05-29 | 2025-05-30 | QA | High | 58 | 62 | Scope Clarification | 2025-05-11 | 2025-05-24 | 10 | Yes | 1
APT-0614 | Customer Onboarding Automation | Sprint 02 - 2025 | Rohan Gupta | High | 3 | In Progress | 2025-01-20 | 2025-01-28 |  | Engineering | Low | 17 | 12 | Resource Constraint | 2025-01-19 | 2025-02-01 | 0 | Yes | 0
APT-0615 | Customer Onboarding Automation | Sprint 06 - 2025 | Vikram Singh | Medium | 3 | Done | 2025-03-22 | 2025-03-27 | 2025-03-29 | Customer Success | Low | 14 | 16 | Resource Constraint | 2025-03-16 | 2025-03-29 | 6 | Yes | 1
APT-0616 | User Access Governance | Sprint 08 - 2025 | Dev Patel | High | 13 | Done | 2025-04-17 | 2025-04-27 | 2025-04-25 | Data Analytics | High | 96 | 141 | None | 2025-04-13 | 2025-04-26 | 7 | No | 1
APT-0617 | API Reliability Upgrade | Sprint 07 - 2025 | Zoya Fernandes | Medium | 2 | Done | 2025-04-04 | 2025-04-15 | 2025-04-15 | Product | Low | 10 | 11 | None | 2025-03-30 | 2025-04-12 | 10 | No | 1
APT-0618 | User Access Governance | Sprint 05 - 2025 | Aarav Mehta | Low | 5 | Done | 2025-03-06 | 2025-03-10 | 2025-03-10 | Data Analytics | Low | 20 | 17 | None | 2025-03-02 | 2025-03-15 | 3 | No | 1
APT-0619 | Mobile Experience Improvements | Sprint 01 - 2025 | Dev Patel | High | 1 | Done | 2025-01-07 | 2025-01-13 | 2025-01-13 | QA | Medium | 5 | 5 | None | 2025-01-05 | 2025-01-18 | 5 | No | 1
APT-0620 | Data Quality Remediation | Sprint 03 - 2025 | Ananya Rao | Medium | 3 | To Do | 2025-02-02 | 2025-02-11 |  | Data Analytics | Low | 16 | 0 | Environment Issue | 2025-02-02 | 2025-02-15 | 0 | Yes | 0

## Dataset Summary
Metric | Value
Total Tasks | 620
Completed Tasks | 450
Pending Tasks | 170
Completion Rate | 0.72581
Average Cycle Time | 6.92
Overdue Tasks | 354
High Risk Tasks | 119

## Sprint Summary
Sprint Name | Total Tasks | Completed Tasks | Planned Story Points | Completed Story Points | Completion Rate
Sprint 01 - 2025 | 45 | 34 | 222 | 172 | 0.75556
Sprint 02 - 2025 | 49 | 35 | 237 | 173 | 0.71429
Sprint 03 - 2025 | 49 | 36 | 179 | 138 | 0.73469
Sprint 04 - 2025 | 47 | 33 | 214 | 161 | 0.70213
Sprint 05 - 2025 | 55 | 46 | 226 | 188 | 0.83636
Sprint 06 - 2025 | 53 | 44 | 216 | 187 | 0.83019
Sprint 07 - 2025 | 51 | 38 | 239 | 162 | 0.7451
Sprint 08 - 2025 | 54 | 39 | 256 | 189 | 0.72222
Sprint 09 - 2025 | 55 | 34 | 238 | 129 | 0.61818
Sprint 10 - 2025 | 57 | 45 | 267 | 218 | 0.78947
Sprint 11 - 2025 | 59 | 42 | 255 | 181 | 0.71186
Sprint 12 - 2025 | 46 | 24 | 147 | 76 | 0.52174